## Requirements Register
ORACLE EPM WFP — REQUIREMENTS REGISTER ¦ Position-Based Planning ¦ Release 1a
Req ID | Category | Sub-Category | Short Description | Full Requirement | Sprint | Priority | Oracle EPM Cloud Configuration Approach
WF-01 | Governance & Controls | Version Control | Version control for cost centre structures | Cost center hierarchies must be centrally governed and version-controlled. Ability to plan, promote, and enact a version with a new cost centre structure. | Design & Align | P1-Must Have | Oracle Planning: LCM Lifecycle Management for hierarchy snapshots. Admin → Dimension Editor: Cost Centre hierarchy versioned via Named Sets. Promote via Admin → Application Management → Migration.
WF-02 | Governance & Controls | Version Control | Approval process for Final budget changes | Once a Final budget version is approved, any subsequent changes must require top-of-house approval. Approval process tagging enforced. | S1 | P1-Must Have | Oracle Planning: Planning Unit Hierarchy → Top-of-house owner. Approval workflow: Status = 'Approved' locks version. Override requires Admin role + SteerCo change request. Business Rules: CUST_VersionLock checks status before allowing edit.
WF-13 | Governance & Controls | Baseline Data | Traceability to Management Hierarchy | Workforce Planning must support traceability of data to the Management View (Accounts). | Design & Align | P1-Must Have | Oracle Planning: Alternate hierarchy 'Management_View' on Account dimension. Smart View: XREF formula maps GL account → management category. Narrative Reporting: management grouping dimension filter on all WFP reports.
WF-14 | Governance & Controls | Baseline Data | Traceability to data source | Workforce Planning must support traceability of data source (e.g., Workday, PeopleFluent, manual input). Attribute on each data cell. | S2 | P1-Must Have | Oracle Planning: Custom attribute 'Data_Source' on Account or separate dimension member. EPM Data Management: load jobs stamp source tag. CUST_DataSourceTag Groovy: marks manual overrides vs system-loaded data.
WF-41 | Governance & Controls | Version Control | Formal version progression Baseline→Working→Final | System must enforce formal version progression: Baseline → Working → Final, with controlled submission and approval at each stage. Promote scenario selected by dept leadership. | S1 | P1-Must Have | Oracle Planning: Version dimension — Baseline (locked, read-only), Working (open submission), Draft_1/2, Final (locked post-approval). Planning Unit Hierarchy: status transitions enforced. Business Rule: CUST_VersionPromotion copies Working→Draft on submit.
WF-51 | Governance & Controls | Baseline Data | Traceable and explainable calculations | Workforce calculations must be traceable and explainable. Ability to see component details of the workforce modelling and costing logic. | S3 | P1-Must Have | Oracle Planning: Supporting Detail on all Groovy calc outputs. Calc Manager: Business Rule logic visible in Calc Manager console. Narrative Reporting: drill-through from summary → position → calc component.
WF-88 | Governance & Controls | Baseline Data | Lock baseline — no auto-refresh once planning begins | Ability to lock data once planning or forecasting begins ensuring baseline data is not automatically refreshed when a monthly data run happens. | S2 | P1-Must Have | Oracle Planning: Version 'Baseline' set to locked status after Q-minus-1 snapshot. EPM Automate: load job checks version lock flag before writing. CUST_BaselineLock Business Rule: rejects EPM DM writes to locked version.
WF-19 | Position-Based Planning | Planning Functionality | Position-based planning (below MD) + employee-based (MD+) | Workforce planning must support position-based planning with traceability to employees. Staff below MD: position-based. MD and above: employee-based (actual salary, individual Employee ID). | Design & Align | P1-Must Have | Oracle Planning WFP module: Enable Position-Based Planning. Dimension: Position ID as sparse dimension. WF-19: position-employee linkage. WF-84: MD+ planning at Employee_ID level. Custom form: Position_Planning_Form with employee drill-through. Security: MD+ employee data restricted to HR Admin + CFO roles.
WF-84 | Position-Based Planning | Planning Functionality | MD+ employee-level planning (individual salary) | System must support planning for MD and above roles at the individual Employee ID level (actual salary), not Position ID level. Restricted access to defined user group. | S1 | P1-Must Have | Oracle Planning: MD+ flag on Grade dimension member. CUST_MDPlusPlanning Groovy: when Grade_Flag = 'MD+', source from Employee_ID actual salary. Security: Job Role 'MD_Planner' restricted to Finance_Admin + CHRO. Data Access Filter: Employee dimension filtered by role assignment.
WF-28 | Position-Based Planning | Position Structure | Position lifecycle statuses (unfilled/filled/pending) | The Workforce Planning application must support position lifecycle statuses (unfilled, filled, pending) to support planning and forecasting logic. | S1 | P1-Must Have | Oracle Planning WFP: Position Status attribute — values: Filled, Unfilled, Pending_Hire, On_Leave, Pipeline. Custom attribute on Position dimension. CUST_PositionLifecycle Groovy: routes calc logic based on Status. Forms: status-driven conditional formatting.
WF-31 | Position-Based Planning | Planning Functionality | Open new / inactivate existing positions (attrition) | System must allow users to inactivate/close approved open roles for a fiscal year (roles not filled) while retaining the record for tracking and history. | S4 | P1-Must Have | Oracle Planning WFP: Position Status → Closed_Attrition. CUST_PositionAttrition Groovy: zeroes comp from effective close month; retains position member in hierarchy for history. Form: Attrition_Planning_Form with effective date input. Reports: track closed positions for retrospective analysis.
WF-37 | Position-Based Planning | Scenarios | Pipeline / proposed positions during budgeting | System must allow proposed (unapproved) positions during planning and forecasting. Create planned pipeline roles, map to open/filled actuals once established in Workday. | S4 | P1-Must Have | Oracle Planning WFP: Position Status = Pipeline. CUST_PipelinePosition: calculates partial-year cost from proposed hire date. Integration: nightly match job — when Workday creates matching position, auto-update status to Filled and link Employee_ID. Pending positions visible in Position_Planning_Form with distinct color coding.
WF-52 | Position-Based Planning | Planning Functionality | Committed vs uncommitted (open) position costs | System should distinguish committed vs uncommitted (open) position costs. | S4 | P2-Should Have | Oracle Planning: Custom account members — 'Committed_Cost' (filled positions) vs 'Uncommitted_Cost' (approved open positions). CUST_CommittedFlag Groovy: routes cost to committed/uncommitted account based on Position_Status. Dashboard tile: committed vs uncommitted split by dept.
WF-50 | Position-Based Planning | Edge Cases | Double-occupancy prevention (shared position HC=1) | Ability to prevent double counting when two employees temporarily occupy one position (e.g., shadowing, maternity/leave). Headcount must remain at 1; costing may reflect temporary overlap. | S3 | P1-Must Have | Oracle Planning WFP: Position attribute 'Double_Occupancy_Flag'. CUST_DoubleOccupancyCheck Groovy: if Flag=Y, HC count capped at 1 for FTE metric; compensation calc sums both employee salaries for cost period. Supporting Detail: both employee IDs logged on position.
WF-64 | Position-Based Planning | Security | Drill from filled position to employee | Authorized users must be able to drill from a filled position to identify the employee tagged to that position, ensuring traceability from position to employee. | S4 | P1-Must Have | Oracle Planning WFP: Position_Employee_Link dimension attribute. Forms: Smart View drill-through from Position_ID → Employee_ID detail. Security: Job Role 'HR_Admin' and 'Finance_Admin' only. Audit log: drill-through access tracked in EPM access log.
WF-92 | Position-Based Planning | Edge Cases | Retirement planning — reserve cost + reallocate dollars | Plan retirements and reserve planned cost for entire year, creating ability to reallocate. Position: termination removes Employee_ID linkage, position becomes open. Deferred/VDIP costs to central cost centre. | S4 | P2-Should Have | Oracle Planning WFP: Retirement_Flag on position. CUST_RetirementCalc: full-year cost reserved until effective retirement date then zeroed. CUST_VDIPDeferral: moves deferred ICP to Central_CC post-retirement. Form: retirement date input with deferred amount calculation visible.
WF-20 | Metadata / Dimensions | Hierarchy | Consistent CC naming — employees-only cost centres | WFP application must only include cost centers that house employees, not the full GL hierarchy. Must reflect same naming convention as source systems. | Design & Align | P1-Must Have | Oracle Planning: Separate WFP_CostCentre hierarchy (subset of GL CC hierarchy). EPM DM: filter load to include only CCs with Employee_Count > 0. Admin → Dimension Editor: alternate hierarchy 'WFP_CC' maps to Workday OrgUnit naming. Nightly sync: add/remove CCs based on Workday OrgUnit active flag.
WF-32 | Metadata / Dimensions | Hierarchy | Financial vs. Management hierarchies for personnel costs | System must support separate Financial (GL) and Management hierarchies for personnel-related expenses. Both must reconcile to totals. | Design & Align | P1-Must Have | Oracle Planning: Two alternate hierarchies on Entity + Account dimensions — 'Financial_View' (GL/statutory) and 'Management_View'. Smart View: hierarchy selector for ad-hoc. Narrative Reporting: separate data sources per view. CUST_HierarchyReconcile: validates Financial_Total = Management_Total.
WF-21 | Metadata / Dimensions | Dimensions | Location as dimension (not attribute) | Location must be modeled as a dimension, not an attribute. | Design & Align | P1-Must Have | Oracle Planning: 'Location' as sparse dimension — not a UDA/attribute. Members: Country → Region → City → Office. Used in: CUST_HKHousingAllowance, CUST_FXTranslation, CUST_IntlAssignment. Size optimization: keep Location sparse to avoid BSO block creation.
WF-26 | Metadata / Dimensions | Dimensions | Project dimension for future cube integration | A Project dimension must be available to support future integration with Project cube. | Design & Align | P2-Should Have | Oracle Planning: 'Project' dimension — stub hierarchy for Release 1a (NoProject + TBD members). Future: EPM Data Management integration with Project Planning cube. Dimension type: sparse, generic. Release 1b: full project-workforce cost mapping.
WF-27 | Metadata / Dimensions | Dimensions | Version dimension — Enterprise and What-If categories | Version dimension must support two distinct categories: Enterprise versions (Working, Drafts, Final) and What-If versions. | S1 | P1-Must Have | Oracle Planning: Version dimension members — Enterprise: Baseline, Working, Draft_1, Draft_2, Final. What-If: WhatIf_A, WhatIf_B, WhatIf_C, WhatIf_D, WhatIf_E (5 max). UDA: 'Enterprise' vs 'WhatIf' tag for filtering. CUST_VersionLifecycle enforces stage transitions.
WF-22 | Metadata / Dimensions | Scenarios | Version lifecycle management — limited, managed | Number of plan/forecast versions must be limited and lifecycle-managed. Up to 5 What-If scenarios, not maintained after cycle closes unless promoted. | S1 | P1-Must Have | Oracle Planning: Annual version cleanup job via EPM Automate — archive What-If versions after cycle close. CUST_VersionArchive: promotes selected What-If to named version or deletes. Admin: version count enforced — max 5 What-If concurrent. Audit log: promotion history retained.
WF-23 | Metadata / Dimensions | Dimensions | Dimension optimization for application performance | Application performance must be optimized by optimizing dimension size. | Design & Align | P1-Must Have | Oracle Planning BSO/ASO design: Dense dimensions — Account + Period. Sparse — Entity, Department, Position, Scenario, Version, Location, Job. Keep Position hierarchy shallow. Aggregate storage option (ASO) for reporting cube. CUST_BlockCleanup: auto-clear empty blocks on WFPClearAll.
WF-25 | Metadata / Dimensions | Dimensions | Multi-currency — regional/local currency + FX impact | WFP application must be multi-currency enabled. Record salary in regional/local currency, complete regional analyses, see FX impact. | S1 | P1-Must Have | Oracle Planning: Enable currency in Application Settings. Reporting Currency: CAD. Input currencies per location: USD, GBP, HKD, BRL, EUR. Exchange rate table: FX_Rates[Currency, Year, Type=Annual_Avg]. CUST_FXTranslation Groovy: Local_Amount × FX_Rate[Currency, FY].
WF-33 | Metadata / Dimensions | Hierarchy | Personnel cost categories not driven by positions | System must support personnel-related cost categories not driven by positions or employees (e.g., severance, payroll admin, employee acquisition) while included in overall personnel cost envelope. | Design & Align | P1-Must Have | Oracle Planning: Account dimension — 'Personnel_NonPosition' sub-hierarchy: Severance, Payroll_Admin, Employee_Acquisition, Employer_Taxes. These accounts planned directly (not driven by position count). Forms: separate Non-Position_Personnel_Form. Reconcile into total Personnel_Cost account.
WF-34 | Metadata / Dimensions | Position Structure | Contingent costs linked to positions (or position-less) | System must support linking contingent workforce costs to positions where applicable (backfills, temp replacements), while also allowing position-less contingent costs. | S3 | P2-Should Have | Oracle Planning: Position attribute 'Contingent_Link' — FK to Position_ID if backfill. CUST_ContractorCost: if Contingent_Link = position, cost allocated to that position's cost centre. If position-less: allocated to dept-level Contingent_Pool account. Form: contingent entry with optional Position_Link field.
WF-35 | Metadata / Dimensions | Commentary | Commentary at planning steps — stored in Oracle | Ability to capture commentary directly in Oracle (rationale, explanations, notes) and store for audit and reporting purposes when drivers are changed. | S4 | P1-Must Have | Oracle Planning: Cell Text / Supporting Detail on all planning forms. Narrative Reporting: NR report includes commentary column pulled from Planning cell text. EPM Data Management: commentary exported in data extract for audit evidence. Form design: mandatory commentary field when value deviates > threshold.
WF-36 | Metadata / Dimensions | Commentary | Standardized commentary categories + file attachments | Standardize commentary categories (e.g., FX, rates, attrition, vacancy, realization) and enable file attachments. Commentary must be reportable and auditable. | S4 | P1-Must Have | Oracle Planning: Custom list: Commentary_Category UDA on cell text (FX / Rates / Attrition / Vacancy / Realization / Other). File attachment: Oracle Planning Document Library linked to planning units. Narrative Reporting: filter commentary by category for audit report.
WF-30 | Metadata / Dimensions | Data | Turnover definition — departures only, not internal moves | Solution must maintain standard definitions: turnover = departures from organization, does not include internal role moves (to avoid mislabeling and incorrect logic). | Design & Align | P1-Must Have | Oracle Planning: Account dimension — 'Turnover' account = external departures only. Separate account 'Internal_Transfer' for role moves. CUST_TurnoverCalc: sources from Workday Turnover_Events dimension (Resignation + Involuntary); excludes Position_Transfer events. Driver table: Turnover_Rate[Dept] = Turnover_Events / Avg_Filled_HC.
WF-29 | Metadata / Dimensions | Position Structure | Worker type dimension — Regular/Intern/Secondment/Contingent | WFP must support capability to plan at worker type level: regular, intern, secondment, contingent. | Design & Align | P1-Must Have | Oracle Planning: 'Worker_Type' dimension — Regular_FTE, Intern, Secondment, Contingent_Vendor, Contingent_Backfill. Used by: CUST_MeritEligibility (excludes Interns/Contingent), CUST_BenefitsCalc (FT vs PT rates), CUST_ContractorCost. Position attribute linked to Worker_Type.
WF-24 | Metadata / Dimensions | Position Structure | Job and grade structures aligned with Workday | Job and grade structures must align with Workday definitions. | S2 | P1-Must Have | Oracle Planning: Job_Code and Grade dimensions loaded from Workday Job Profile extract. EPM DM: HRIS_JobGrade_Load job — Workday Job Profile → Oracle Job_Code hierarchy. Nightly sync: delta load for new jobs/grades. Validation: CUST_JobGradeValidation checks Job_Code exists in Workday before accepting planning entries.
WF-10 | Data | Actuals Data | Workday as SOR for positions (via Talent Data Product) | Workday must remain the system of record for positions, grades, and employee attributes via the Talent Data Product — monthly snapshot consumption. | S2 | P1-Must Have | EPM Data Management: Talent_Data_Product_Load job — consumes monthly position snapshot from Talent Data Product. Workday → Talent Data Product (Data Fabric/SCD) → EPM. Job: HRIS_Position_Snapshot_Monthly. Validation: position count reconciliation before EPM write. SOR rules: no manual position creation in EPM without Workday source record.
WF-15 | Data | Actuals Data | PeopleFluent ICP data via Talent Data Product | WFP must consume Incentive Compensation (ICP) data sourced from PeopleFluent via the Talent Data Product. | S2 | P1-Must Have | EPM DM: PeopleFluent_ICP_Load — ICP assumptions (Target Bonus%, In-Year ICP%, Deferred%, RoR) from Talent Data Product. Load frequency: monthly. Mapping: PeopleFluent employee → Oracle Position_ID. ICP assumption table in Oracle Planning: ICP_Rates[Position_ID, Scenario, Period]. Used by WF-74/75/76 Groovy rules.
WF-17 | Data Integration | Actuals Data | Automated file ingestion — reduced manual preprocessing | WFP must support automated file ingestion with reduced manual preprocessing. | S2 | P1-Must Have | EPM Automate: scheduled job triggers EPM Data Management batch. File format: standardized CSV/Parquet from Talent Data Product API. Pre-processing: Python Lambda validates schema before EPM load. Error quarantine: invalid files held in staging — not rejected outright. EPM DM transformation: column mapping, null handling, FX translation applied automatically.
WF-16 | Data Integration | Reports - Audit | Validate source data + error report + re-trigger | WFP must support a full-and-final inbound data load — load completes only if all required data is successfully processed. | S2 | P1-Must Have | EPM DM: 'All-or-Nothing' load mode — if any record fails validation, entire load rolled back. Error Report: auto-generated HTML/CSV report with failed records, field-level errors, rule violation details. Shared to Data_Ops team email list. Manual re-trigger: EPM Automate 'rerun_load' command after corrections. WF-11: invalid combos (CC vs Location mismatch) flagged as load failure.
WF-11 | Data Integration | Reports - Audit | Detect invalid combinations — mark file load as failed | System must detect invalid data combinations (e.g., cost center vs location mismatch) and mark the entire file load as failed. | S2 | P1-Must Have | EPM DM: Cross-reference validation rule — CC_Location_Matrix table. If CC not in Location's valid set → load flagged as failed. Error report: flags all invalid combos with record count. CUST_DataValidation Business Rule: post-load integrity check on Position_CC_Location triples.
WF-12 | Data | Actuals Data | More frequent workforce data refresh | Workforce data refresh must support more frequent forecasting (sub-monthly refreshes). | S2 | P2-Should Have | EPM Automate: on-demand load trigger available via REST API or manual EPM Automate command. Talent Data Product: supports delta extract (changed records only) for mid-cycle refresh. CUST_DeltaLoad: appends changed positions without full reload. Governance: mid-cycle refresh logged in audit trail with timestamp and requester.
WF-65 | Data | Actuals Data | Actual salary from Talent Data Product at position level | Actual salary data fetched from Talent Data Product and loaded at position level. System calculates average salary by Sub-Dept, Location, Role, Grade (and consolidated at Role level). | S2 | P1-Must Have | EPM DM: Actual_Salary_Load — Position_ID, Actual_Annual_Salary from Talent Data Product. Average calc: CUST_AvgSalaryByMatrix computes Avg[Sub_Dept, Location, Role, Grade] and stores in assumption table. Used as input to WF-68/WF-69 base pay calcs. Refresh: monthly with Workday snapshot.
WF-08 | Data | Historical Data | 5+ years historical actuals readily available | System must support tiered historical data retention (hot/warm/cold) to balance performance, calculation needs, and long-term reference requirements. | S2 | P1-Must Have | Oracle Planning: Hot tier — FY22-FY25 actuals in active Planning cube (full calc access). Warm tier — FY20-FY21 in reporting-only cube (ASO). Cold tier — FY15-FY19 archived in EPM Cloud data files (extract on demand). EPM Automate: annual tier migration job. Recalculation disabled on cold tier.
WF-09 | Data | Historical Data | 5 years actuals + prior-year budget/forecast — no recalc | System must retain at least five years of historical actuals and prior-year approved budget/forecast for reporting and comparison purposes, without recalculation. | S2 | P1-Must Have | Oracle Planning: Historical actuals stored in locked 'Actuals' scenario — no calc rules fire on locked periods. Prior-year Budget/Forecast retained in dedicated Year members (FY22_Budget, FY23_Budget, etc.). Reporting cube (ASO): all 5 years accessible for variance trending.
WF-05 | Data | Hierarchy | Historical data restatements to current hierarchy | System must support controlled historical restatement to current hierarchies for reporting, with clear communication that historical views reflect today's structure. | S2 | P2-Should Have | Oracle Planning: Restatement process — copy historical actuals to 'Restated' version with new hierarchy mapping. CUST_HistoricalRestatement: maps old CC → new CC per reorg mapping table. Reports: label restated data clearly. Original historical version preserved (immutable). Governance: restatement requires Finance Lead approval.
WF-49 | Data | Baseline Data | Latest forecast as baseline for annual planning | Ability to use the latest Forecast as standardized baseline for Annual Planning (e.g., if Q2 is latest, use Q2; later use Q3 when available). | S2 | P1-Must Have | Oracle Planning: CUST_BaselineRefresh — copies latest available Forecast version to 'Baseline' version. EPM Automate: scheduled job checks for new forecast availability and triggers refresh. Governance: baseline refresh requires PMO approval and is logged. Lock: baseline locked once Annual Budget cycle opens.
WF-95 | Data Integration | General Functionality | Push from calc module (WFP) to reporting module | System pushes data from final versions to necessary reporting module. Leveraging current data model structure: push from WFP calc cube to REP reporting cube and FS module. | S4 | P1-Must Have | Oracle Planning: EPM Automate job 'Push_WFP_to_REP' — copies approved WFP version data to Reporting cube. User-triggered: form button 'Submit to Reporting' — fires EPM Automate without BI team involvement, by dept. Push to FS module: 'Push_WFP_to_FS' job copies personnel costs to Financial Statement cube for aggregation.
WF-06 | Scenarios | Planning Functionality | New cost centre structure without overwriting historical | System must support reorg planning without overwriting historical actuals. Plan, promote, and enact version with new CC structure. | S1 | P1-Must Have | Oracle Planning: Scenario 'Reorg_Sandbox' with experimental CC hierarchy. LCM snapshot of current hierarchy before reorg enactment. CUST_ReorgMapping: maps employees/positions from old CC → new CC effective date. History: original CC actuals preserved; restated view available via WF-05 process.
WF-07 | Scenarios | Planning Functionality | Confidential experimental CC structures — pre/post comparison | Users must be able to compare pre- and post-reorg structures. Confidential experimentation. | S4 | P2-Should Have | Oracle Planning: What-If scenario with restricted visibility (WF-59 security). CUST_ReorgComparison: side-by-side view — current hierarchy vs proposed hierarchy. Dashboard: Reorg_Comparison_Dashboard with pre/post cost and HC deltas. Access: only Finance_Admin and requesting Dept Head.
WF-38 | Scenarios | Planning Functionality | Up to 5 What-If scenarios — not maintained after cycle unless promoted | Future system to have capability to support What-If Analysis through version dimensions. Up to 5 saved named scenarios with different driver compositions. | S1 | P1-Must Have | Oracle Planning: Version dimension What-If members: WhatIf_A through WhatIf_E. CUST_WhatIfCreate: copies Working version to What-If on user request. EPM Automate: end-of-cycle cleanup archives or deletes What-If versions. Promotion: CUST_VersionPromotion copies selected What-If to named permanent version.
WF-39 | Scenarios | Planning Functionality | Top-down and bottom-up planning by version | Application must support top-down and bottom-up planning approaches by version. | S4 | P1-Must Have | Oracle Planning: Top-Down version — envelope loaded at Division level by CFO; dept planners see constraint, distribute bottom-up. Bottom-Up version — dept planners build freely; consolidated for CFO review. CUST_TopDownBottomUpReconcile: highlights variance between TD and BU versions on CFO dashboard.
WF-40 | Scenarios | Planning Functionality | Side-by-side A/B/C version comparison | System must support side-by-side comparison of multiple versions (e.g., A/B/C) based on different driver or position assumptions. | S4 | P2-Should Have | Oracle Planning: Smart View ad-hoc grid — multi-version axis. Dashboard: Scenario_Comparison_Dashboard showing WhatIf_A vs WhatIf_B vs Working on key metrics (Total_Comp, Total_FTE, OPEX_Total). CUST_ScenarioVariance: outputs pairwise delta for each comparison set.
WF-42 | Scenarios | Drivers | Vacancy as calculated output (not flat rate input) | System must treat vacancy as a calculated output: approved positions vs filled positions over time, not a single flat-rate input. | S3 | P1-Must Have | Oracle Planning: CUST_VacancyCalc — Vacancy = Approved_HC − Filled_HC per position per period. Driver-based: vacancy driven by turnover events + hiring pipeline (not input). Vacancy_Rate = Vacancy / Approved_HC. Monthly trending visible in dashboard. WF-44: turnover applied to filled positions only.
WF-43 | Scenarios | Calculations | Decomposed vacancy model — vacancy months + cost impact | System must support decomposed vacancy model: driven by turnover events + hiring pipeline/time-to-fill. Vacancy quantified as vacancy months and translated to cost impact. | S3 | P1-Must Have | Oracle Planning: CUST_VacancyDecomposed — Vacancy_Months = sum(days_vacant / days_in_period) per position. Vacancy_Cost = Avg_Monthly_Salary × Vacancy_Months. Components: Turnover_Vacancy (resigned/terminated), Pipeline_Vacancy (open approved roles), Fill_Lag_Vacancy (time-to-fill). Dashboard: vacancy waterfall by component.
WF-44 | Scenarios | Drivers | Turnover rate applied to filled positions only | System must apply turnover rates only to filled positions (bums-in-seats), not to already-vacant approved positions. | S3 | P1-Must Have | Oracle Planning: CUST_TurnoverCalc — filter: IF Position_Status = 'Filled' THEN apply Turnover_Rate ELSE 0. Driver table: Turnover_Rate[Dept, Worker_Type, Year]. Turnover event: creates vacancy months from effective departure date. Does not apply to unfilled approved positions.
WF-45 | Scenarios | Drivers | Attrition — vacancy not replaced, headcount reduces | System must support attrition as distinct concept: positions vacant and intentionally not replaced, reducing headcount over time. | S4 | P1-Must Have | Oracle Planning: Attrition_Flag on position. CUST_AttritionCalc: IF Attrition_Flag = Y, position status → Closed_Attrition; HC count decremented from effective month; cost zeroed. Distinct from Turnover (replaced) vs Attrition (not replaced). Reports: attrition tracker by dept with HC impact.
WF-47 | Scenarios | Edge Cases | Contingent workforce costs — distinct category | System must support planning and visibility of contingent workforce costs as distinct category within personnel-related costs, separate from permanent employees. | S3 | P2-Should Have | Oracle Planning: Account hierarchy — 'Personnel_Contingent' sub-hierarchy. Worker_Type dimension: Contingent_Vendor, Contingent_Backfill. CUST_ContractorCost: Bill_Rate × Hours × Utilization%. Dashboard: FTE vs Contingent cost split. WF-57: comparative analysis FTE vs contingent trade-off.
WF-48 | Scenarios | Edge Cases | Time-bound contingent planning (start/end dates) | System must support time-bound contingent workforce planning (start/end dates) to reflect temporary nature. | S3 | P2-Should Have | Oracle Planning: Position attribute Start_Date, End_Date for contingent roles. CUST_ContingentTimeBound: zeroes cost outside start/end range. Period spread: only active months included. Form: Contingent_Planning_Form with mandatory start/end date fields.
WF-54 | Scenarios | Planning Functionality | Effective-dated movements — transfers, promotions, leavers | WFP must support analysis of headcount and cost movements (transfers, promotions, leavers) with effective dates. | S4 | P1-Must Have | Oracle Planning WFP: Effective-date attribute on Position. CUST_EffectiveDateCalc: prorate cost from effective month. Movement types: Transfer (CC change), Promotion (grade change), Departure (effective end date). CUST_MovementAnalysis: HC movement waterfall — opening → new hires → transfers_in → transfers_out → promotions → departures → closing.
WF-55 | Scenarios | Planning Functionality | Departmental envelopes visible during planning | During forecasting, system must display approved annual budget build-up number as reference alongside forecast results. Ability to input and change envelopes. | S4 | P1-Must Have | Oracle Planning: Top_Down_Envelope loaded to 'Budget_Envelope' account member. Planning form: envelope displayed as read-only reference column beside forecast input. CUST_EnvelopeVariance: flags dept forecast > envelope. CFO can update envelope with change tracking. Form: Budget_Envelope_Form (Finance_Admin access only).
WF-56 | Scenarios | Drivers | Vacancy actionable via underlying drivers and trending | Solution must provide reporting/trending that makes vacancy actionable by exposing underlying drivers: turnover, fill rates, external hires, internal fills, recruitment velocity, time-to-fill. | S4 | P2-Should Have | Oracle Planning: Vacancy_Driver_Dashboard — waterfall chart showing: Opening_Vacant + New_Turnover − External_Hires − Internal_Fills = Closing_Vacant. KPI tiles: Avg_Time_to_Fill, Fill_Rate, Turnover_Rate trending MoM. CUST_VacancyDriverReconcile: ensures components sum to total vacancy.
WF-57 | Scenarios | Edge Cases | Contingent vs FTE cost trade-off comparison | System must enable comparative analysis of contingent workforce vs FTE cost trade-offs to support staffing decisions (e.g., convert contractor to FTE). | S4 | P2-Should Have | Oracle Planning: What-If scenario — copy current position as Contingent_Option vs FTE_Option. CUST_FTEvContingentCompare: outputs fully-loaded FTE cost vs contractor cost (incl. benefits premium, mgmt overhead vs bill rate premium). Dashboard: comparative table with break-even analysis.
WF-80 | Scenarios | Planning Functionality | Transfer between cost centres — no approval workflow required | System must allow direct transfer of employees between cost centers without requiring formal approval workflow prior to processing. | S4 | P2-Should Have | Oracle Planning: CUST_CCTransfer Groovy — moves employee linkage from old CC to new CC effective from specified month. No approval gate required (distinguishes from structural reorg which requires governance). Audit log: transfer recorded with date, old CC, new CC, requester. HC counts updated immediately in both CCs.
WF-82 | Scenarios | Planning Functionality | Termination/departure effective from specified month | System must allow users to plan a termination/departure effective from a specified month, with salary and related costs stopping from that month onward. | S4 | P1-Must Have | Oracle Planning WFP: CUST_TerminationLogic — input: Position_ID + Effective_Term_Month. Logic: zero all comp accounts from effective month onward. Severance: Severance_Cost = Base_Salary × Severance_Weeks/52 loaded to Severance account in effective month. FTE count: decremented from effective month. Position status → Filled_to_Vacant.
WF-86 | Scenarios | Time Horizon | 3-year monthly planning horizon | System must support preparation of budgets over a three-year planning horizon. | Design & Align | P1-Must Have | Oracle Planning: Year dimension — Current_Year + Year+1 + Year+2 + Year+3. Monthly granularity for all 3 years. Period dimension: 36 months active planning horizon. CUST_LongRangeForecast: assumption roll-forward for years 2-3 (escalation factors applied). Dashboard: 3-year trend view on HC and Comp.
WF-93 | Scenarios | Planning Functionality | Planners adjust driver-related inputs | Ability for planners to adjust driver-related inputs to calculations, including trend-based drivers. | S4 | P1-Must Have | Oracle Planning: Driver assumption forms — open for planner input per planning unit. Drivers: Merit_Pct, COLA_Pct, Turnover_Rate, Time_to_Fill, Benefit_Rates. Lock mechanism: drivers locked at version promotion. Governance: driver changes > ±X% flagged and require commentary (WF-35/36). Audit trail: all driver changes logged.
WF-97 | Scenarios | Scenario Planning | Dynamic hierarchy group selection — see only selected groups | Ability for planners to select specific groups within their hierarchy level and dynamically see the associated plans and budget dollars for only those selected groups. | S4 | P2-Should Have | Oracle Planning: Smart View: member selector for ad-hoc hierarchy filtering. Planning forms: user-defined subset prompts on Entity and Department dimensions. Dashboard: dynamic filter tiles — planner selects dept/entity subset, dashboard refreshes to show only selected scope. EPM Groovy: prompt-based variable substitution.
WF-58 | Security | Employee Data | Confidentiality throughout integration pipeline | WFP must ensure confidentiality of workforce data across entire integration process — from source systems through Talent Data Product into EPBCS. | Design & Align | P1-Must Have | EPM DM: TLS 1.3 in transit; AES-256 at rest. Talent Data Product: field-level encryption for salary and ICP data. Oracle Planning: no clear-text storage of employee PII. EPM access log: all data access events logged. Compliance: data classification tags on all sensitive dimensions.
WF-59 | Security | Planning Functionality | Sensitive scenarios with restricted visibility | System must allow sensitive scenarios to be created and analyzed with restricted visibility from other users. | S1 | P1-Must Have | Oracle Planning: What-If versions with group-based access restriction. Job Role: Scenario_Owner has read/write; others have no access. EPM Security: data access filter on Version dimension by user group. Sensitive scenarios: Reorg_Scenario, MD+ planning, ICP sensitivity analysis — each has dedicated restricted role.
WF-60 | Security | Employee Data | Role- and dimension-based security for planning users | System must support role- and dimension-based data security to protect sensitive workforce data while enabling planning users to perform their responsibilities. | S1 | P1-Must Have | Oracle Planning: 5 job roles — Planner (dept-level only), Reviewer (read all, approve own), Finance_Admin (full), HR_Admin (employee data), Read_Only (CFO/exec view). Data access filter: Dept dimension filtered per user's cost centre assignment. Row-level security on Position dimension.
WF-61 | Security | Employee Data | Anonymity thresholds for small teams | System must support anonymity thresholds (e.g., minimum headcount) to prevent inference of individual compensation in small teams or cost centers. | S4 | P2-Should Have | Oracle Planning: CUST_AnonymityCheck — if Filled_HC < 3 in any CC/Grade combination, suppress individual comp detail; display aggregated amount only. Narrative Reporting: minimum headcount filter on position-level reports. Dashboard: position detail hidden for sub-threshold CCs.
WF-62 | Security | Employee Data | Restricted access to MD+ compensation and ICP assumptions | System must support restricted access to sensitive compensation elements (MD+ components, ICP assumptions) independent of cost centre access. | S1 | P1-Must Have | Oracle Planning: Data access filter on Account dimension — MD_Comp accounts (MD_Base, MD_ICP, MD_Bonus) restricted to HR_Admin + Finance_Admin roles. ICP assumption table: Job Role 'ICP_Manager' (HR Comp team only). Segregated from cost centre security — MD comp hidden even for dept Finance Lead.
WF-63 | Security | Employee Data | Dimension-level security — Account, CC, Job, Employee, Version | System must support dimension-level security applied across: Account, Cost Center, Job, Employee, and Version, to control data visibility based on user role. | S1 | P1-Must Have | Oracle Planning Security: Data Access Filters (DAFs) per dimension. Account DAF: role-based account hierarchy visibility. Cost Center DAF: user-to-CC mapping table. Job DAF: confidential job families restricted. Employee DAF: planner sees own dept employees only. Version DAF: What-If visibility per scenario owner.
WF-03 | Reports / Views | Reports - Audit | Audit report — changes between versions | System must maintain an audit trail of changes between versions, including what changed and (where applicable) why via associated commentary. | S4 | P1-Must Have | Oracle Planning: Built-in audit log — Admin → Audit. Custom: CUST_AuditReport Groovy compares Version_A vs Version_B at cell level and outputs delta report. Narrative Reporting: NR_Audit_Report template with commentary pulled from cell text. EPM Automate: weekly audit report export to SharePoint for compliance.
WF-04 | Reports / Views | Reports - Financial | Management reporting distinct from financial reporting | System must support clear classification rules: Personnel vs G&A costs for management reporting, without altering statutory financial reporting. | S4 | P1-Must Have | Oracle Planning: Alternate account hierarchy — 'Management_View' (Personnel / G&A / ICP) vs 'Financial_View' (GL accounts). CUST_MgmtReportClassify: routes costs to correct management category. Narrative Reporting: separate NR reports per view. Smart View: Management_View vs Financial_View toggle.
WF-53 | Reports / Views | Reports - Audit | Reconciliation checkpoints — WFP vs Financial/Reporting | Application must provide reconciliation checkpoints between Workforce Planning and Financial/Reporting views. | S4 | P1-Must Have | Oracle Planning: CUST_WFPtoFSReconcile — compares Personnel_Total in WFP cube vs FS cube. Reconciliation report: automated variance table — WFP_Total, FS_Total, Difference, Tolerance_Flag. Dashboard tile: reconciliation RAG status. EPM Automate: nightly reconcile job with alert on variance > threshold.
WF-87 | Reports / Views | Reports - BOR | Budget Objective Report — WFP + FS cube combined | System must support generation of a Budget Objective Report utilizing calculated data from both the Workforce Planning cube and the Financials (FS) cube. | S4 | P1-Must Have | Oracle Planning: BOR report uses FDMEE cross-cube extract. Narrative Reporting: BOR_Report template with embedded Smart View queries to both WFP and FS cubes. Security: role-based distribution — each dept sees only their own rollup. EPM Automate: trigger BOR generation post-Final version approval.
WF-96 | Reports / Views | Reports - Variance | Variance — prior period actuals vs prior forecast and budget | Ability to see variance when comparing previous period actuals against previous period forecast and budget. | S4 | P2-Should Have | Oracle Planning: Variance accounts: Actual_vs_Budget = Actual − Budget; Actual_vs_Forecast = Actual − Forecast; Prior_Period_Variance. CUST_VarianceCalc: computed monthly. Smart View: prior-period variance template. Narrative Reporting: NR_Variance_Report with period-over-period waterfall.
WF-68 | Business Logic / Calculations | Base Pay | CALC: Avg Monthly Salary — Approved Filled Positions | System must calculate Average Monthly Salary as Average of Annual Salary at Sub Dept, Location, Role and Worker Type / 12 for Approved Positions. | S3 | P1-Must Have | CUST_AvgMonthlySalary_Filled Groovy: Avg_Monthly_Salary = AVG(Annual_Salary[Sub_Dept, Location, Role, Worker_Type]) / 12 for positions where Status = Filled. Sources: Actual_Salary_Load from Talent Data Product (WF-65). Stored to: Planning assumption table AMS_Matrix[Sub_Dept, Location, Role, Worker_Type].
WF-69 | Business Logic / Calculations | Base Pay | CALC: Avg Monthly Salary — New Pending Positions (midpoint fallback) | System must calculate Average Monthly Salary for New Pending Positions. If average not available, use Midpoint data received from Talent Data Product. | S3 | P1-Must Have | CUST_AvgMonthlySalary_Pending Groovy: IF AMS_Matrix[Sub_Dept, Location, Role, Worker_Type] exists THEN use average ELSE use Midpoint[Home_Location, Level] from Talent Data Product (WF-66). Logic: first check AMS_Matrix; if null, fallback to Midpoint table. Null guard: if both null, flag for Finance review.
WF-66 | Business Logic / Calculations | Base Pay | CALC: Midpoint salary from Talent Data Product | Midpoint salary must be fetched from Talent Data Product by Home Location and Level to support annual salary calculations during planning and forecasting. | S2 | P1-Must Have | EPM DM: Midpoint_Load job — source: Talent Data Product midpoint extract by Home_Location + Level. Target: Oracle Planning assumption table Midpoint[Home_Location, Level]. Refresh: monthly with compensation band updates. Used by: CUST_AvgMonthlySalary_Pending (WF-69) as fallback.
WF-70 | Business Logic / Calculations | Merit Pay | CALC: Merit increase from merit month with effective date | System must calculate Merit increase as Monthly Salary × Merit% starting from defined merit month. | S3 | P1-Must Have | CUST_MeritCalc Groovy: Merit_Cost_Monthly = Avg_Monthly_Salary × Merit_Pct[Grade, Year] for months >= Merit_Month. Pre-merit months: no merit increment. Merit_Month configured per planning cycle in assumption table. Cumulative: April merit → compound for remainder of year. Output: Merit_Cost account per position per period.
WF-71 | Business Logic / Calculations | Merit Pay | CALC: Merit exclusion — newly promoted positions | Merit calculation must not apply to Newly Promoted Positions. | S3 | P1-Must Have | CUST_MeritExclusion Groovy: IF Promotion_Flag = Y AND Promotion_Year = Current_Year THEN Merit_Pct = 0. Promotion flag set by CUST_PromotionCalc. Logic: newly promoted employees receive promotion increment instead of merit increment in the same year. Flag auto-reset to N at fiscal year start.
WF-83 | Business Logic / Calculations | Merit Pay | CALC: Merit eligibility — exclude Interns and Contingent | Merit should not apply to Interns and Contingent workers; merit only applies to eligible employee types. | S3 | P1-Must Have | CUST_MeritEligibility Groovy: Merit_Pct = 0 IF Worker_Type IN ('Intern', 'Contingent_Vendor', 'Contingent_Backfill'). Eligibility table: Merit_Eligible_Flag[Worker_Type] — Regular_FTE=Y, Secondment=configurable, Intern=N, Contingent=N. Applied before CUST_MeritCalc runs.
WF-72 | Business Logic / Calculations | Benefits | CALC: Salary benefits — (Salary + Merit) × Blended Benefits% | System must calculate Salary Benefits using (Salary + Merit) × Blended Benefits%. | S3 | P1-Must Have | CUST_BenefitsCalc Groovy: Benefits_Cost = (Avg_Monthly_Salary + Merit_Cost_Monthly) × Blended_Benefit_Rate[Worker_Type, Location]. Benefit_Rate table: FT_CAD=28%, PT_CAD=15%, HK=22%, BRL=35% (statutory). Includes: CPP, EI, WSIB, Group Health, Pension match. Does not include ICP benefits (handled by WF-75).
WF-81 | Business Logic / Calculations | Promotions | CALC: Promotion salary impact — Average Monthly Salary × Promotion% | System must calculate promotion impact as Average Monthly Salary × Promotion%, stored separately for tracking and reporting. | S3 | P1-Must Have | CUST_PromotionCalc Groovy: Promotion_Cost = Avg_Monthly_Salary × Promotion_Rate[Dept, Grade]. Stored to dedicated 'Promotion_Increment' account (separate from Base_Salary). Promotion_Rate: Talent Data Product driver (WF-15). Sets Promotion_Flag=Y for WF-71 merit exclusion. Output: visible in position detail for audit.
WF-85 | Business Logic / Calculations | Base Pay | CALC: Salary roll-forward — last month AMS → next year base | Merit-adjusted average monthly salary in last month of fiscal year must automatically roll forward and become base (average monthly salary) for subsequent budget year. | S3 | P1-Must Have | CUST_SalaryRollForward Groovy: Next_Year_Base_Salary = AMS_Month_12 (last month of current FY including merit). Runs: post-Final version lock, pre-new-year planning open. Stores: to AMS_Matrix for new fiscal year. Merit compound: ensures prior-year merit is baked into new-year starting base.
WF-74 | Business Logic / Calculations | ICP | CALC: ICP In-Year Gross Amount | System must calculate ICP In-Year Gross Amount based on Annual Salary × ICP% × Multiplier Factor. | S3 | P1-Must Have | CUST_ICPInYear Groovy: ICP_InYear_Gross = Annual_Salary × ICP_Target_Pct × Total_Fund_Multiplier × Individual_Multiplier. Drivers sourced from PeopleFluent via Talent Data Product (WF-67): ICP_Target_Pct, Total_Fund_Multiplier, Individual_Multiplier, Departmental_Multiplier. Stored: ICP_InYear_Gross account per position.
WF-75 | Business Logic / Calculations | ICP | CALC: ICP In-Year Merit and associated benefits on merit-adjusted salary | System must calculate ICP In-Year Merit and associated benefits based on merit-adjusted salary. | S3 | P1-Must Have | CUST_ICPMeritBenefits Groovy: ICP_Merit_Component = (Salary + Merit_Cost) × ICP_Pct × Multiplier. Benefits on ICP: ICP_Benefits = ICP_InYear_Gross × Benefit_Rate_ICP[Worker_Type]. Stored separately from base benefits (WF-72). Allows ICP cost to be tracked as distinct component in management reporting.
WF-76 | Business Logic / Calculations | ICP | CALC: Deferred ICP — current and prior years with compounding RoR | System must calculate Deferred ICP amounts (current year and prior years) including compounding using applicable Rate of Return factors. | S3 | P1-Must Have | CUST_ICPDeferred Groovy: Deferred_ICP_CY = ICP_InYear_Gross × Deferred_Pct. Deferred_ICP_PY_Compound = Deferred_ICP_PY × (1 + RoR_Factor). Total_Deferred = Deferred_ICP_CY + Deferred_ICP_PY_Compound. RoR_Factor: Total_Fund_RoR from PeopleFluent. Prior year balances carried forward from EPM historical actuals.
WF-67 | Business Logic / Calculations | ICP | CALC: ICP drivers from PeopleFluent via Talent Data Product | System must retrieve ICP drivers and assumptions (Target Bonus%, In-Year ICP%, Deferred%, components) from PeopleFluent via Talent Data Product. | S2 | P1-Must Have | EPM DM: ICP_Assumptions_Load — source: PeopleFluent via Talent Data Product. Target table: ICP_Assumption_Form in Oracle Planning. Fields: ICP_Target_Pct[Position_ID], In_Year_ICP_Pct, Deferred_Pct, Fund_Multiplier, PI_Multiplier, Dept_Multiplier, Total_Fund_RoR, PI_RoR. Refresh: monthly sync with quarterly quarterly cycle snapshot.
WF-77 | Business Logic / Calculations | VDIP | CALC: Fund VDIP and PI VDIP — compounding to payout year | System must calculate Fund VDIP and PI VDIP (in-year and prior-year balances) including compounding logic until payout year. | S3 | P2-Should Have | CUST_VDIPCalc Groovy: Fund_VDIP_InYear = ICP_InYear_Gross × VDIP_Pct. PI_VDIP_InYear = ICP_InYear_Gross × PI_VDIP_Pct. Compounding: VDIP_Balance_t = VDIP_Balance_(t-1) × (1 + Fund_RoR) + VDIP_InYear_t. Payout year: VDIP_Payout = VDIP_Balance at defined vest date. Multiple vintages tracked: VDIP_2022, VDIP_2023, VDIP_2024 balances.
WF-73 | Business Logic / Calculations | HK and BRL | CALC: Location-specific components — HK Housing + BRL statutory | System must calculate location-specific salary components: HK Housing Allowance (fixed rate, existing employees only) and BRL statutory elements (13th month, vacation bonuses). | S3 | P2-Should Have | CUST_HKHousingAllowance Groovy: IF Location = HK AND Worker_Type = Regular_FTE AND Position_Status != New_Hire THEN Housing_Allow = Fixed_HK_Rate. Excludes new hires and open positions. CUST_BRLStatutory: 13th_Month = BRL_Monthly_Salary; Vacation_Bonus = BRL_Monthly_Salary × (1/3). Applied to all BRL positions.
WF-78 | Business Logic / Calculations | HK and BRL | CALC: BRL statutory ICP — 13th month, deferred, vacation bonus | System must calculate BRL statutory ICP-related bonuses (13th month, deferred, vacation bonus) derived from gross and deferred ICP components. | S3 | P2-Should Have | CUST_BRLStatutoryICP Groovy: BRL_ICP_13th = ICP_InYear_Gross / 12. BRL_ICP_Deferred_Vacation = Deferred_ICP_CY × (1/3). Total_BRL_ICP_Statutory = BRL_ICP_13th + BRL_ICP_Deferred_Vacation. Applies only to: Location = BRL. Used for payroll cost estimation in BRL planning.
WF-79 | Business Logic / Calculations | FX | CALC: FX translation — Local Currency to CAD (annual average rate) | System must support FX translation from Local Currency to CAD using annual average rate. | S3 | P1-Must Have | CUST_FXTranslation Groovy: CAD_Amount = Local_Amount × FX_Rate[Currency, FY, Rate_Type='Annual_Avg']. Rate table: FX_Rates[Currency, Year] loaded from EPM DM (FX data feed or manual input). Currencies: USD, GBP, HKD, BRL, EUR → CAD. Reporting: both local currency and CAD views available via currency toggle.
WF-90 | Business Logic / Calculations | International Assignments | CALC: International assignment — legal entity FX and cost treatment | Ability to reference legal entity to determine proper treatment of International Assignments (expats) and their respective currency within a cost centre. | S3 | P2-Should Have | CUST_IntlAssignmentCalc Groovy: reads Legal_Entity attribute on position. IF Position has Intl_Assignment_Flag AND Home_Entity ≠ Host_Entity: cost split per assignment agreement (host vs home CC). FX: apply Host_Currency FX rate for local costs; Home_Currency for net-back. Attribute: Intl_Assignment_Type (Short-term / Long-term / Secondment).
WF-91 | Business Logic / Calculations | Mumbai | CALC: Mumbai cost categorization — salary/benefits reconciliation | Mapping capability that reconciles the cost categorization issue of salary/benefits for Mumbai. | S3 | P2-Should Have | CUST_MumbaiCostMapping Groovy: IF Location = Mumbai THEN apply Mumbai_Cost_Category_Mapping table — maps statutory salary + benefits components to correct Oracle account. Mumbai-specific: PF (Provident Fund) mapped to Benefits_Statutory; Gratuity mapped to Benefits_LongTerm; Professional_Tax mapped to Employer_Taxes. Reconciles to GL account mapping.
WF-89 | Business Logic / Calculations | Base Pay | CALC: Partial month — expected hire date for open roles | Ability to utilize incoming expected hire date for open roles in planning & forecasting to support partial month calculations. | S3 | P1-Must Have | CUST_PartialMonthCalc Groovy: IF Position_Status = Open AND Expected_Hire_Date is set THEN Monthly_Cost = Full_Monthly_Cost × (Days_Remaining_in_Month / Days_in_Month) for hire month. Subsequent months: full monthly cost. Hire date input: Expected_Hire_Date field on Position_Planning_Form. Cascade: all downstream calcs (merit, benefits, ICP) prorated from hire month.
WF-43+ | Business Logic / Calculations | Vacancy | CALC: Vacancy decomposed — turnover + pipeline + time-to-fill | Decomposed vacancy model: vacancy months from turnover events + hiring pipeline/time-to-fill, translated to cost impact. | S3 | P1-Must Have | CUST_VacancyDecomposed Groovy: Turnover_Vacancy_Months = Σ(days_vacant_post_departure / period_days). Pipeline_Vacancy_Months = Σ(days_unfilled_approved_open / period_days). Total_Vacancy_Months = Turnover_Vacancy + Pipeline_Vacancy. Vacancy_Savings = Avg_Monthly_Salary × Total_Vacancy_Months. Components stored as separate account members for drill-through.
WF-ADV-01 | Business Logic / Calculations | ICP Sensitivity | ICP actuals calc with sensitivity analysis (RoR impact) | Calculate ICP actuals in EPBCS based on ICP assumptions (Total Fund Multiplier, Total Fund RoR, PI RoR, Individual/Departmental Multiplier, FX rates, headcount). Sensitivity: if RoR +10%, what is ICP impact? | S3 | P2-Should Have | CUST_ICPSensitivity Groovy: creates What-If ICP scenario with RoR +/-Δ%. Sensitivity range: ±5%, ±10%, ±15% on Total_Fund_RoR and PI_RoR. Output: ICP_Sensitivity_Table[RoR_Δ, ICP_Impact_$, ICP_Impact_%]. Dashboard: sensitivity tornado chart on ICP total.
WF-ADV-02 | Business Logic / Calculations | Mass Changes | Mass changes — bulk headcount transactions in single UI action | Ability to transact and update multiple roles at one time within a department and mass submit to Oracle (transfers, promotions, start/end dates, role changes, type changes). | S4 | P2-Should Have | Oracle Planning: CUST_MassUpdate Groovy — accepts array input from mass-change form. Form: Mass_Change_Form with multi-row grid, checkboxes for position selection, bulk field update (effective date, new CC, new grade, new worker type). Submit: single EPM rule invocation updates all selected rows. Audit log: bulk update recorded as batch transaction.
WF-ADV-03 | Business Logic / Calculations | Manual Adjustments | Manual salary adjustment — override for specific position | Ability to adjust specific salary used for an employee or open role and downstream calculations use that adjusted number. | S4 | P1-Must Have | Oracle Planning: Manual_Salary_Override flag on Position form. CUST_ManualOverrideCalc: IF Override_Flag = Y THEN use Override_Salary ELSE use AMS from matrix. Override_Salary input cell (blue, editable). Downstream: all calc rules (Merit, Benefits, ICP, VDIP) cascade from Override_Salary when flag set. Audit: override logged with requester, old value, new value.
WF-ADV-04 | Metadata / Dimensions | Hierarchy Management | Centrally managed hierarchies — aligned with all source systems | Any data warehouse/source (Data Fabric/SCD, Oracle Financials) integrated with ETL tool to ensure metadata/hierarchies updated. Oracle Financials CC Hierarchy + Account Hierarchies aligned. | S2 | P1-Must Have | EPM DM: Hierarchy_Sync_Load job — source: Oracle Financials CC Hierarchy via Data Fabric. Nightly delta load: adds new CCs, renames changed, marks deleted as inactive. Oracle Planning: Admin hierarchy refresh post-load. LCM snapshot before each hierarchy sync. Alert: hierarchy change email notification to Finance_Admin.
WF-ADV-05 | Scenarios | Long Range | 3–5 year cost projection on rolling basis | Ability to update assumptions and headcount profile into future long-range plan years (current year +2/+3/+4/+5) on rolling basis if required and have system cost appropriately. | S4 | P2-Should Have | Oracle Planning: Year dimension — Year+1 through Year+5. CUST_LongRangeForecast: applies escalation factors for years 3-5 (Headcount_Growth%, Salary_Escalation%, Benefit_Rate_Trend%). Assumption table: LRP_Drivers[Year, Factor]. Dashboard: 5-year HC and Comp trend chart. EPM Automate: annual LRP refresh job.
WF-ADV-06 | Data Integration | Push to Reporting | User-triggered push: WFP calc module → REP WFP reporting module | User should be able to push data from calc (CLC WFP) module to reporting (REP WFP) without requiring BI team. Can trigger by dept. | S4 | P1-Must Have | Oracle Planning: EPM Automate 'Push_to_REP' job exposed via Planning form button (no BI team needed). Dept-level scope: user selects their dept, push runs for that dept only. Copy: CUST_WFPtoREP copies approved version to REP cube. Confirmation: success toast notification on form. Audit log: push timestamp, user, dept, version.
WF-ADV-07 | Data Integration | Push to FS | User-triggered push: WFP calc module → FS module for aggregation | User should be able to push data from calc (CLC WFP) to FS module (Financial Statement) for aggregation. By dept, without BI team. | S4 | P1-Must Have | Oracle Planning: EPM Automate 'Push_to_FS' job — user-triggered from Planning form. Dept-level: maps WFP Personnel accounts to FS Personnel accounts. CUST_WFPtoFS Groovy: validates reconciliation before write (WF-53). Confirmation: reconciliation report auto-generated post-push. FS cube: receives Personnel_Total by CC, Period, Scenario.

## Sprint Plan — Requirements
SPRINT-MAPPED REQUIREMENTS ¦ Position-Based Planning ¦ Oracle EPM WFP Release 1a
▶ DESIGN & ALIGN — Jan–Feb 2025 — Architecture, dimension design, governance frameworks, position-based planning design [13 requirements]
# | Req ID | Category | Short Description | Oracle EPM Config (Summary) | Priority
1 | WF-01 | Governance & Controls Version Control | Version control for cost centre structures | Oracle Planning: LCM Lifecycle Management for hierarchy snapshots. Admin → Dimension Editor: Cost Centre hierarchy versioned via Named Sets. Promote via Admin → Application Managem | P1-Must Have
2 | WF-13 | Governance & Controls Baseline Data | Traceability to Management Hierarchy | Oracle Planning: Alternate hierarchy 'Management_View' on Account dimension. Smart View: XREF formula maps GL account → management category. Narrative Reporting: management groupin | P1-Must Have
3 | WF-19 | Position-Based Planning Planning Functionality | Position-based planning (below MD) + employee-based (MD+) | Oracle Planning WFP module: Enable Position-Based Planning. Dimension: Position ID as sparse dimension. WF-19: position-employee linkage. WF-84: MD+ planning at Employee_ID level. | P1-Must Have
4 | WF-20 | Metadata / Dimensions Hierarchy | Consistent CC naming — employees-only cost centres | Oracle Planning: Separate WFP_CostCentre hierarchy (subset of GL CC hierarchy). EPM DM: filter load to include only CCs with Employee_Count > 0. Admin → Dimension Editor: alternate | P1-Must Have
5 | WF-32 | Metadata / Dimensions Hierarchy | Financial vs. Management hierarchies for personnel costs | Oracle Planning: Two alternate hierarchies on Entity + Account dimensions — 'Financial_View' (GL/statutory) and 'Management_View'. Smart View: hierarchy selector for ad-hoc. Narrat | P1-Must Have
6 | WF-21 | Metadata / Dimensions Dimensions | Location as dimension (not attribute) | Oracle Planning: 'Location' as sparse dimension — not a UDA/attribute. Members: Country → Region → City → Office. Used in: CUST_HKHousingAllowance, CUST_FXTranslation, CUST_IntlAss | P1-Must Have
7 | WF-26 | Metadata / Dimensions Dimensions | Project dimension for future cube integration | Oracle Planning: 'Project' dimension — stub hierarchy for Release 1a (NoProject + TBD members). Future: EPM Data Management integration with Project Planning cube. Dimension type: | P2-Should Have
8 | WF-23 | Metadata / Dimensions Dimensions | Dimension optimization for application performance | Oracle Planning BSO/ASO design: Dense dimensions — Account + Period. Sparse — Entity, Department, Position, Scenario, Version, Location, Job. Keep Position hierarchy shallow. Aggre | P1-Must Have
9 | WF-33 | Metadata / Dimensions Hierarchy | Personnel cost categories not driven by positions | Oracle Planning: Account dimension — 'Personnel_NonPosition' sub-hierarchy: Severance, Payroll_Admin, Employee_Acquisition, Employer_Taxes. These accounts planned directly (not dri | P1-Must Have
10 | WF-30 | Metadata / Dimensions Data | Turnover definition — departures only, not internal moves | Oracle Planning: Account dimension — 'Turnover' account = external departures only. Separate account 'Internal_Transfer' for role moves. CUST_TurnoverCalc: sources from Workday Tur | P1-Must Have
11 | WF-29 | Metadata / Dimensions Position Structure | Worker type dimension — Regular/Intern/Secondment/Contingent | Oracle Planning: 'Worker_Type' dimension — Regular_FTE, Intern, Secondment, Contingent_Vendor, Contingent_Backfill. Used by: CUST_MeritEligibility (excludes Interns/Contingent), CU | P1-Must Have
12 | WF-86 | Scenarios Time Horizon | 3-year monthly planning horizon | Oracle Planning: Year dimension — Current_Year + Year+1 + Year+2 + Year+3. Monthly granularity for all 3 years. Period dimension: 36 months active planning horizon. CUST_LongRangeF | P1-Must Have
13 | WF-58 | Security Employee Data | Confidentiality throughout integration pipeline | EPM DM: TLS 1.3 in transit; AES-256 at rest. Talent Data Product: field-level encryption for salary and ICP data. Oracle Planning: no clear-text storage of employee PII. EPM access | P1-Must Have
▶ S1 — Mar 2025 — Environment, metadata load, version control, security, position lifecycle, 5 std Oracle rules [13 requirements]
# | Req ID | Category | Short Description | Oracle EPM Config (Summary) | Priority
1 | WF-02 | Governance & Controls Version Control | Approval process for Final budget changes | Oracle Planning: Planning Unit Hierarchy → Top-of-house owner. Approval workflow: Status = 'Approved' locks version. Override requires Admin role + SteerCo change request. Business | P1-Must Have
2 | WF-41 | Governance & Controls Version Control | Formal version progression Baseline→Working→Final | Oracle Planning: Version dimension — Baseline (locked, read-only), Working (open submission), Draft_1/2, Final (locked post-approval). Planning Unit Hierarchy: status transitions e | P1-Must Have
3 | WF-84 | Position-Based Planning Planning Functionality | MD+ employee-level planning (individual salary) | Oracle Planning: MD+ flag on Grade dimension member. CUST_MDPlusPlanning Groovy: when Grade_Flag = 'MD+', source from Employee_ID actual salary. Security: Job Role 'MD_Planner' res | P1-Must Have
4 | WF-28 | Position-Based Planning Position Structure | Position lifecycle statuses (unfilled/filled/pending) | Oracle Planning WFP: Position Status attribute — values: Filled, Unfilled, Pending_Hire, On_Leave, Pipeline. Custom attribute on Position dimension. CUST_PositionLifecycle Groovy: | P1-Must Have
5 | WF-27 | Metadata / Dimensions Dimensions | Version dimension — Enterprise and What-If categories | Oracle Planning: Version dimension members — Enterprise: Baseline, Working, Draft_1, Draft_2, Final. What-If: WhatIf_A, WhatIf_B, WhatIf_C, WhatIf_D, WhatIf_E (5 max). UDA: 'Enterp | P1-Must Have
6 | WF-22 | Metadata / Dimensions Scenarios | Version lifecycle management — limited, managed | Oracle Planning: Annual version cleanup job via EPM Automate — archive What-If versions after cycle close. CUST_VersionArchive: promotes selected What-If to named version or delete | P1-Must Have
7 | WF-25 | Metadata / Dimensions Dimensions | Multi-currency — regional/local currency + FX impact | Oracle Planning: Enable currency in Application Settings. Reporting Currency: CAD. Input currencies per location: USD, GBP, HKD, BRL, EUR. Exchange rate table: FX_Rates[Currency, Y | P1-Must Have
8 | WF-06 | Scenarios Planning Functionality | New cost centre structure without overwriting historical | Oracle Planning: Scenario 'Reorg_Sandbox' with experimental CC hierarchy. LCM snapshot of current hierarchy before reorg enactment. CUST_ReorgMapping: maps employees/positions from | P1-Must Have
9 | WF-38 | Scenarios Planning Functionality | Up to 5 What-If scenarios — not maintained after cycle unless promoted | Oracle Planning: Version dimension What-If members: WhatIf_A through WhatIf_E. CUST_WhatIfCreate: copies Working version to What-If on user request. EPM Automate: end-of-cycle clea | P1-Must Have
10 | WF-59 | Security Planning Functionality | Sensitive scenarios with restricted visibility | Oracle Planning: What-If versions with group-based access restriction. Job Role: Scenario_Owner has read/write; others have no access. EPM Security: data access filter on Version d | P1-Must Have
11 | WF-60 | Security Employee Data | Role- and dimension-based security for planning users | Oracle Planning: 5 job roles — Planner (dept-level only), Reviewer (read all, approve own), Finance_Admin (full), HR_Admin (employee data), Read_Only (CFO/exec view). Data access f | P1-Must Have
12 | WF-62 | Security Employee Data | Restricted access to MD+ compensation and ICP assumptions | Oracle Planning: Data access filter on Account dimension — MD_Comp accounts (MD_Base, MD_ICP, MD_Bonus) restricted to HR_Admin + Finance_Admin roles. ICP assumption table: Job Role | P1-Must Have
13 | WF-63 | Security Employee Data | Dimension-level security — Account, CC, Job, Employee, Version | Oracle Planning Security: Data Access Filters (DAFs) per dimension. Account DAF: role-based account hierarchy visibility. Cost Center DAF: user-to-CC mapping table. Job DAF: confid | P1-Must Have
▶ S2 — Apr 2025 — All integrations (Workday/Talent DP/PeopleFluent), data loads, baseline governance [17 requirements]
# | Req ID | Category | Short Description | Oracle EPM Config (Summary) | Priority
1 | WF-14 | Governance & Controls Baseline Data | Traceability to data source | Oracle Planning: Custom attribute 'Data_Source' on Account or separate dimension member. EPM Data Management: load jobs stamp source tag. CUST_DataSourceTag Groovy: marks manual ov | P1-Must Have
2 | WF-88 | Governance & Controls Baseline Data | Lock baseline — no auto-refresh once planning begins | Oracle Planning: Version 'Baseline' set to locked status after Q-minus-1 snapshot. EPM Automate: load job checks version lock flag before writing. CUST_BaselineLock Business Rule: | P1-Must Have
3 | WF-24 | Metadata / Dimensions Position Structure | Job and grade structures aligned with Workday | Oracle Planning: Job_Code and Grade dimensions loaded from Workday Job Profile extract. EPM DM: HRIS_JobGrade_Load job — Workday Job Profile → Oracle Job_Code hierarchy. Nightly sy | P1-Must Have
4 | WF-10 | Data Actuals Data | Workday as SOR for positions (via Talent Data Product) | EPM Data Management: Talent_Data_Product_Load job — consumes monthly position snapshot from Talent Data Product. Workday → Talent Data Product (Data Fabric/SCD) → EPM. Job: HRIS_Po | P1-Must Have
5 | WF-15 | Data Actuals Data | PeopleFluent ICP data via Talent Data Product | EPM DM: PeopleFluent_ICP_Load — ICP assumptions (Target Bonus%, In-Year ICP%, Deferred%, RoR) from Talent Data Product. Load frequency: monthly. Mapping: PeopleFluent employee → Or | P1-Must Have
6 | WF-17 | Data Integration Actuals Data | Automated file ingestion — reduced manual preprocessing | EPM Automate: scheduled job triggers EPM Data Management batch. File format: standardized CSV/Parquet from Talent Data Product API. Pre-processing: Python Lambda validates schema b | P1-Must Have
7 | WF-16 | Data Integration Reports - Audit | Validate source data + error report + re-trigger | EPM DM: 'All-or-Nothing' load mode — if any record fails validation, entire load rolled back. Error Report: auto-generated HTML/CSV report with failed records, field-level errors, | P1-Must Have
8 | WF-11 | Data Integration Reports - Audit | Detect invalid combinations — mark file load as failed | EPM DM: Cross-reference validation rule — CC_Location_Matrix table. If CC not in Location's valid set → load flagged as failed. Error report: flags all invalid combos with record c | P1-Must Have
9 | WF-12 | Data Actuals Data | More frequent workforce data refresh | EPM Automate: on-demand load trigger available via REST API or manual EPM Automate command. Talent Data Product: supports delta extract (changed records only) for mid-cycle refresh | P2-Should Have
10 | WF-65 | Data Actuals Data | Actual salary from Talent Data Product at position level | EPM DM: Actual_Salary_Load — Position_ID, Actual_Annual_Salary from Talent Data Product. Average calc: CUST_AvgSalaryByMatrix computes Avg[Sub_Dept, Location, Role, Grade] and stor | P1-Must Have
11 | WF-08 | Data Historical Data | 5+ years historical actuals readily available | Oracle Planning: Hot tier — FY22-FY25 actuals in active Planning cube (full calc access). Warm tier — FY20-FY21 in reporting-only cube (ASO). Cold tier — FY15-FY19 archived in EPM | P1-Must Have
12 | WF-09 | Data Historical Data | 5 years actuals + prior-year budget/forecast — no recalc | Oracle Planning: Historical actuals stored in locked 'Actuals' scenario — no calc rules fire on locked periods. Prior-year Budget/Forecast retained in dedicated Year members (FY22_ | P1-Must Have
13 | WF-05 | Data Hierarchy | Historical data restatements to current hierarchy | Oracle Planning: Restatement process — copy historical actuals to 'Restated' version with new hierarchy mapping. CUST_HistoricalRestatement: maps old CC → new CC per reorg mapping | P2-Should Have
14 | WF-49 | Data Baseline Data | Latest forecast as baseline for annual planning | Oracle Planning: CUST_BaselineRefresh — copies latest available Forecast version to 'Baseline' version. EPM Automate: scheduled job checks for new forecast availability and trigger | P1-Must Have
15 | WF-66 | Business Logic / Calculations Base Pay | CALC: Midpoint salary from Talent Data Product | EPM DM: Midpoint_Load job — source: Talent Data Product midpoint extract by Home_Location + Level. Target: Oracle Planning assumption table Midpoint[Home_Location, Level]. Refresh: | P1-Must Have
16 | WF-67 | Business Logic / Calculations ICP | CALC: ICP drivers from PeopleFluent via Talent Data Product | EPM DM: ICP_Assumptions_Load — source: PeopleFluent via Talent Data Product. Target table: ICP_Assumption_Form in Oracle Planning. Fields: ICP_Target_Pct[Position_ID], In_Year_ICP_ | P1-Must Have
17 | WF-ADV-04 | Metadata / Dimensions Hierarchy Management | Centrally managed hierarchies — aligned with all source systems | EPM DM: Hierarchy_Sync_Load job — source: Oracle Financials CC Hierarchy via Data Fabric. Nightly delta load: adds new CCs, renames changed, marks deleted as inactive. Oracle Plann | P1-Must Have
▶ S3 — May 2025 — All compensation, ICP, VDIP, HC driver, FX, location-specific Groovy calc rules [28 requirements]
# | Req ID | Category | Short Description | Oracle EPM Config (Summary) | Priority
1 | WF-51 | Governance & Controls Baseline Data | Traceable and explainable calculations | Oracle Planning: Supporting Detail on all Groovy calc outputs. Calc Manager: Business Rule logic visible in Calc Manager console. Narrative Reporting: drill-through from summary → | P1-Must Have
2 | WF-50 | Position-Based Planning Edge Cases | Double-occupancy prevention (shared position HC=1) | Oracle Planning WFP: Position attribute 'Double_Occupancy_Flag'. CUST_DoubleOccupancyCheck Groovy: if Flag=Y, HC count capped at 1 for FTE metric; compensation calc sums both emplo | P1-Must Have
3 | WF-34 | Metadata / Dimensions Position Structure | Contingent costs linked to positions (or position-less) | Oracle Planning: Position attribute 'Contingent_Link' — FK to Position_ID if backfill. CUST_ContractorCost: if Contingent_Link = position, cost allocated to that position's cost ce | P2-Should Have
4 | WF-42 | Scenarios Drivers | Vacancy as calculated output (not flat rate input) | Oracle Planning: CUST_VacancyCalc — Vacancy = Approved_HC − Filled_HC per position per period. Driver-based: vacancy driven by turnover events + hiring pipeline (not input). Vacanc | P1-Must Have
5 | WF-43 | Scenarios Calculations | Decomposed vacancy model — vacancy months + cost impact | Oracle Planning: CUST_VacancyDecomposed — Vacancy_Months = sum(days_vacant / days_in_period) per position. Vacancy_Cost = Avg_Monthly_Salary × Vacancy_Months. Components: Turnover_ | P1-Must Have
6 | WF-44 | Scenarios Drivers | Turnover rate applied to filled positions only | Oracle Planning: CUST_TurnoverCalc — filter: IF Position_Status = 'Filled' THEN apply Turnover_Rate ELSE 0. Driver table: Turnover_Rate[Dept, Worker_Type, Year]. Turnover event: cr | P1-Must Have
7 | WF-47 | Scenarios Edge Cases | Contingent workforce costs — distinct category | Oracle Planning: Account hierarchy — 'Personnel_Contingent' sub-hierarchy. Worker_Type dimension: Contingent_Vendor, Contingent_Backfill. CUST_ContractorCost: Bill_Rate × Hours × U | P2-Should Have
8 | WF-48 | Scenarios Edge Cases | Time-bound contingent planning (start/end dates) | Oracle Planning: Position attribute Start_Date, End_Date for contingent roles. CUST_ContingentTimeBound: zeroes cost outside start/end range. Period spread: only active months incl | P2-Should Have
9 | WF-68 | Business Logic / Calculations Base Pay | CALC: Avg Monthly Salary — Approved Filled Positions | CUST_AvgMonthlySalary_Filled Groovy: Avg_Monthly_Salary = AVG(Annual_Salary[Sub_Dept, Location, Role, Worker_Type]) / 12 for positions where Status = Filled. Sources: Actual_Salary | P1-Must Have
10 | WF-69 | Business Logic / Calculations Base Pay | CALC: Avg Monthly Salary — New Pending Positions (midpoint fallback) | CUST_AvgMonthlySalary_Pending Groovy: IF AMS_Matrix[Sub_Dept, Location, Role, Worker_Type] exists THEN use average ELSE use Midpoint[Home_Location, Level] from Talent Data Product | P1-Must Have
11 | WF-70 | Business Logic / Calculations Merit Pay | CALC: Merit increase from merit month with effective date | CUST_MeritCalc Groovy: Merit_Cost_Monthly = Avg_Monthly_Salary × Merit_Pct[Grade, Year] for months >= Merit_Month. Pre-merit months: no merit increment. Merit_Month configured per | P1-Must Have
12 | WF-71 | Business Logic / Calculations Merit Pay | CALC: Merit exclusion — newly promoted positions | CUST_MeritExclusion Groovy: IF Promotion_Flag = Y AND Promotion_Year = Current_Year THEN Merit_Pct = 0. Promotion flag set by CUST_PromotionCalc. Logic: newly promoted employees re | P1-Must Have
13 | WF-83 | Business Logic / Calculations Merit Pay | CALC: Merit eligibility — exclude Interns and Contingent | CUST_MeritEligibility Groovy: Merit_Pct = 0 IF Worker_Type IN ('Intern', 'Contingent_Vendor', 'Contingent_Backfill'). Eligibility table: Merit_Eligible_Flag[Worker_Type] — Regular_ | P1-Must Have
14 | WF-72 | Business Logic / Calculations Benefits | CALC: Salary benefits — (Salary + Merit) × Blended Benefits% | CUST_BenefitsCalc Groovy: Benefits_Cost = (Avg_Monthly_Salary + Merit_Cost_Monthly) × Blended_Benefit_Rate[Worker_Type, Location]. Benefit_Rate table: FT_CAD=28%, PT_CAD=15%, HK=22 | P1-Must Have
15 | WF-81 | Business Logic / Calculations Promotions | CALC: Promotion salary impact — Average Monthly Salary × Promotion% | CUST_PromotionCalc Groovy: Promotion_Cost = Avg_Monthly_Salary × Promotion_Rate[Dept, Grade]. Stored to dedicated 'Promotion_Increment' account (separate from Base_Salary). Promoti | P1-Must Have
16 | WF-85 | Business Logic / Calculations Base Pay | CALC: Salary roll-forward — last month AMS → next year base | CUST_SalaryRollForward Groovy: Next_Year_Base_Salary = AMS_Month_12 (last month of current FY including merit). Runs: post-Final version lock, pre-new-year planning open. Stores: t | P1-Must Have
17 | WF-74 | Business Logic / Calculations ICP | CALC: ICP In-Year Gross Amount | CUST_ICPInYear Groovy: ICP_InYear_Gross = Annual_Salary × ICP_Target_Pct × Total_Fund_Multiplier × Individual_Multiplier. Drivers sourced from PeopleFluent via Talent Data Product | P1-Must Have
18 | WF-75 | Business Logic / Calculations ICP | CALC: ICP In-Year Merit and associated benefits on merit-adjusted salary | CUST_ICPMeritBenefits Groovy: ICP_Merit_Component = (Salary + Merit_Cost) × ICP_Pct × Multiplier. Benefits on ICP: ICP_Benefits = ICP_InYear_Gross × Benefit_Rate_ICP[Worker_Type]. | P1-Must Have
19 | WF-76 | Business Logic / Calculations ICP | CALC: Deferred ICP — current and prior years with compounding RoR | CUST_ICPDeferred Groovy: Deferred_ICP_CY = ICP_InYear_Gross × Deferred_Pct. Deferred_ICP_PY_Compound = Deferred_ICP_PY × (1 + RoR_Factor). Total_Deferred = Deferred_ICP_CY + Deferr | P1-Must Have
20 | WF-77 | Business Logic / Calculations VDIP | CALC: Fund VDIP and PI VDIP — compounding to payout year | CUST_VDIPCalc Groovy: Fund_VDIP_InYear = ICP_InYear_Gross × VDIP_Pct. PI_VDIP_InYear = ICP_InYear_Gross × PI_VDIP_Pct. Compounding: VDIP_Balance_t = VDIP_Balance_(t-1) × (1 + Fund_ | P2-Should Have
21 | WF-73 | Business Logic / Calculations HK and BRL | CALC: Location-specific components — HK Housing + BRL statutory | CUST_HKHousingAllowance Groovy: IF Location = HK AND Worker_Type = Regular_FTE AND Position_Status != New_Hire THEN Housing_Allow = Fixed_HK_Rate. Excludes new hires and open posit | P2-Should Have
22 | WF-78 | Business Logic / Calculations HK and BRL | CALC: BRL statutory ICP — 13th month, deferred, vacation bonus | CUST_BRLStatutoryICP Groovy: BRL_ICP_13th = ICP_InYear_Gross / 12. BRL_ICP_Deferred_Vacation = Deferred_ICP_CY × (1/3). Total_BRL_ICP_Statutory = BRL_ICP_13th + BRL_ICP_Deferred_Va | P2-Should Have
23 | WF-79 | Business Logic / Calculations FX | CALC: FX translation — Local Currency to CAD (annual average rate) | CUST_FXTranslation Groovy: CAD_Amount = Local_Amount × FX_Rate[Currency, FY, Rate_Type='Annual_Avg']. Rate table: FX_Rates[Currency, Year] loaded from EPM DM (FX data feed or manua | P1-Must Have
24 | WF-90 | Business Logic / Calculations International Assignments | CALC: International assignment — legal entity FX and cost treatment | CUST_IntlAssignmentCalc Groovy: reads Legal_Entity attribute on position. IF Position has Intl_Assignment_Flag AND Home_Entity ≠ Host_Entity: cost split per assignment agreement (h | P2-Should Have
25 | WF-91 | Business Logic / Calculations Mumbai | CALC: Mumbai cost categorization — salary/benefits reconciliation | CUST_MumbaiCostMapping Groovy: IF Location = Mumbai THEN apply Mumbai_Cost_Category_Mapping table — maps statutory salary + benefits components to correct Oracle account. Mumbai-sp | P2-Should Have
26 | WF-89 | Business Logic / Calculations Base Pay | CALC: Partial month — expected hire date for open roles | CUST_PartialMonthCalc Groovy: IF Position_Status = Open AND Expected_Hire_Date is set THEN Monthly_Cost = Full_Monthly_Cost × (Days_Remaining_in_Month / Days_in_Month) for hire mon | P1-Must Have
27 | WF-43+ | Business Logic / Calculations Vacancy | CALC: Vacancy decomposed — turnover + pipeline + time-to-fill | CUST_VacancyDecomposed Groovy: Turnover_Vacancy_Months = Σ(days_vacant_post_departure / period_days). Pipeline_Vacancy_Months = Σ(days_unfilled_approved_open / period_days). Total_ | P1-Must Have
28 | WF-ADV-01 | Business Logic / Calculations ICP Sensitivity | ICP actuals calc with sensitivity analysis (RoR impact) | CUST_ICPSensitivity Groovy: creates What-If ICP scenario with RoR +/-Δ%. Sensitivity range: ±5%, ±10%, ±15% on Total_Fund_RoR and PI_RoR. Output: ICP_Sensitivity_Table[RoR_Δ, ICP_I | P2-Should Have
▶ S4 — Jun 2025 — Advanced scenarios, reporting, BOR, forms, dashboards, NR, SIT readiness [31 requirements]
# | Req ID | Category | Short Description | Oracle EPM Config (Summary) | Priority
1 | WF-31 | Position-Based Planning Planning Functionality | Open new / inactivate existing positions (attrition) | Oracle Planning WFP: Position Status → Closed_Attrition. CUST_PositionAttrition Groovy: zeroes comp from effective close month; retains position member in hierarchy for history. Fo | P1-Must Have
2 | WF-37 | Position-Based Planning Scenarios | Pipeline / proposed positions during budgeting | Oracle Planning WFP: Position Status = Pipeline. CUST_PipelinePosition: calculates partial-year cost from proposed hire date. Integration: nightly match job — when Workday creates | P1-Must Have
3 | WF-52 | Position-Based Planning Planning Functionality | Committed vs uncommitted (open) position costs | Oracle Planning: Custom account members — 'Committed_Cost' (filled positions) vs 'Uncommitted_Cost' (approved open positions). CUST_CommittedFlag Groovy: routes cost to committed/u | P2-Should Have
4 | WF-64 | Position-Based Planning Security | Drill from filled position to employee | Oracle Planning WFP: Position_Employee_Link dimension attribute. Forms: Smart View drill-through from Position_ID → Employee_ID detail. Security: Job Role 'HR_Admin' and 'Finance_A | P1-Must Have
5 | WF-92 | Position-Based Planning Edge Cases | Retirement planning — reserve cost + reallocate dollars | Oracle Planning WFP: Retirement_Flag on position. CUST_RetirementCalc: full-year cost reserved until effective retirement date then zeroed. CUST_VDIPDeferral: moves deferred ICP to | P2-Should Have
6 | WF-35 | Metadata / Dimensions Commentary | Commentary at planning steps — stored in Oracle | Oracle Planning: Cell Text / Supporting Detail on all planning forms. Narrative Reporting: NR report includes commentary column pulled from Planning cell text. EPM Data Management: | P1-Must Have
7 | WF-36 | Metadata / Dimensions Commentary | Standardized commentary categories + file attachments | Oracle Planning: Custom list: Commentary_Category UDA on cell text (FX / Rates / Attrition / Vacancy / Realization / Other). File attachment: Oracle Planning Document Library linke | P1-Must Have
8 | WF-95 | Data Integration General Functionality | Push from calc module (WFP) to reporting module | Oracle Planning: EPM Automate job 'Push_WFP_to_REP' — copies approved WFP version data to Reporting cube. User-triggered: form button 'Submit to Reporting' — fires EPM Automate wit | P1-Must Have
9 | WF-07 | Scenarios Planning Functionality | Confidential experimental CC structures — pre/post comparison | Oracle Planning: What-If scenario with restricted visibility (WF-59 security). CUST_ReorgComparison: side-by-side view — current hierarchy vs proposed hierarchy. Dashboard: Reorg_C | P2-Should Have
10 | WF-39 | Scenarios Planning Functionality | Top-down and bottom-up planning by version | Oracle Planning: Top-Down version — envelope loaded at Division level by CFO; dept planners see constraint, distribute bottom-up. Bottom-Up version — dept planners build freely; co | P1-Must Have
11 | WF-40 | Scenarios Planning Functionality | Side-by-side A/B/C version comparison | Oracle Planning: Smart View ad-hoc grid — multi-version axis. Dashboard: Scenario_Comparison_Dashboard showing WhatIf_A vs WhatIf_B vs Working on key metrics (Total_Comp, Total_FTE | P2-Should Have
12 | WF-45 | Scenarios Drivers | Attrition — vacancy not replaced, headcount reduces | Oracle Planning: Attrition_Flag on position. CUST_AttritionCalc: IF Attrition_Flag = Y, position status → Closed_Attrition; HC count decremented from effective month; cost zeroed. | P1-Must Have
13 | WF-54 | Scenarios Planning Functionality | Effective-dated movements — transfers, promotions, leavers | Oracle Planning WFP: Effective-date attribute on Position. CUST_EffectiveDateCalc: prorate cost from effective month. Movement types: Transfer (CC change), Promotion (grade change) | P1-Must Have
14 | WF-55 | Scenarios Planning Functionality | Departmental envelopes visible during planning | Oracle Planning: Top_Down_Envelope loaded to 'Budget_Envelope' account member. Planning form: envelope displayed as read-only reference column beside forecast input. CUST_EnvelopeV | P1-Must Have
15 | WF-56 | Scenarios Drivers | Vacancy actionable via underlying drivers and trending | Oracle Planning: Vacancy_Driver_Dashboard — waterfall chart showing: Opening_Vacant + New_Turnover − External_Hires − Internal_Fills = Closing_Vacant. KPI tiles: Avg_Time_to_Fill, | P2-Should Have
16 | WF-57 | Scenarios Edge Cases | Contingent vs FTE cost trade-off comparison | Oracle Planning: What-If scenario — copy current position as Contingent_Option vs FTE_Option. CUST_FTEvContingentCompare: outputs fully-loaded FTE cost vs contractor cost (incl. be | P2-Should Have
17 | WF-80 | Scenarios Planning Functionality | Transfer between cost centres — no approval workflow required | Oracle Planning: CUST_CCTransfer Groovy — moves employee linkage from old CC to new CC effective from specified month. No approval gate required (distinguishes from structural reor | P2-Should Have
18 | WF-82 | Scenarios Planning Functionality | Termination/departure effective from specified month | Oracle Planning WFP: CUST_TerminationLogic — input: Position_ID + Effective_Term_Month. Logic: zero all comp accounts from effective month onward. Severance: Severance_Cost = Base_ | P1-Must Have
19 | WF-93 | Scenarios Planning Functionality | Planners adjust driver-related inputs | Oracle Planning: Driver assumption forms — open for planner input per planning unit. Drivers: Merit_Pct, COLA_Pct, Turnover_Rate, Time_to_Fill, Benefit_Rates. Lock mechanism: drive | P1-Must Have
20 | WF-97 | Scenarios Scenario Planning | Dynamic hierarchy group selection — see only selected groups | Oracle Planning: Smart View: member selector for ad-hoc hierarchy filtering. Planning forms: user-defined subset prompts on Entity and Department dimensions. Dashboard: dynamic fil | P2-Should Have
21 | WF-61 | Security Employee Data | Anonymity thresholds for small teams | Oracle Planning: CUST_AnonymityCheck — if Filled_HC < 3 in any CC/Grade combination, suppress individual comp detail; display aggregated amount only. Narrative Reporting: minimum h | P2-Should Have
22 | WF-03 | Reports / Views Reports - Audit | Audit report — changes between versions | Oracle Planning: Built-in audit log — Admin → Audit. Custom: CUST_AuditReport Groovy compares Version_A vs Version_B at cell level and outputs delta report. Narrative Reporting: NR | P1-Must Have
23 | WF-04 | Reports / Views Reports - Financial | Management reporting distinct from financial reporting | Oracle Planning: Alternate account hierarchy — 'Management_View' (Personnel / G&A / ICP) vs 'Financial_View' (GL accounts). CUST_MgmtReportClassify: routes costs to correct managem | P1-Must Have
24 | WF-53 | Reports / Views Reports - Audit | Reconciliation checkpoints — WFP vs Financial/Reporting | Oracle Planning: CUST_WFPtoFSReconcile — compares Personnel_Total in WFP cube vs FS cube. Reconciliation report: automated variance table — WFP_Total, FS_Total, Difference, Toleran | P1-Must Have
25 | WF-87 | Reports / Views Reports - BOR | Budget Objective Report — WFP + FS cube combined | Oracle Planning: BOR report uses FDMEE cross-cube extract. Narrative Reporting: BOR_Report template with embedded Smart View queries to both WFP and FS cubes. Security: role-based | P1-Must Have
26 | WF-96 | Reports / Views Reports - Variance | Variance — prior period actuals vs prior forecast and budget | Oracle Planning: Variance accounts: Actual_vs_Budget = Actual − Budget; Actual_vs_Forecast = Actual − Forecast; Prior_Period_Variance. CUST_VarianceCalc: computed monthly. Smart Vi | P2-Should Have
27 | WF-ADV-02 | Business Logic / Calculations Mass Changes | Mass changes — bulk headcount transactions in single UI action | Oracle Planning: CUST_MassUpdate Groovy — accepts array input from mass-change form. Form: Mass_Change_Form with multi-row grid, checkboxes for position selection, bulk field updat | P2-Should Have
28 | WF-ADV-03 | Business Logic / Calculations Manual Adjustments | Manual salary adjustment — override for specific position | Oracle Planning: Manual_Salary_Override flag on Position form. CUST_ManualOverrideCalc: IF Override_Flag = Y THEN use Override_Salary ELSE use AMS from matrix. Override_Salary inpu | P1-Must Have
29 | WF-ADV-05 | Scenarios Long Range | 3–5 year cost projection on rolling basis | Oracle Planning: Year dimension — Year+1 through Year+5. CUST_LongRangeForecast: applies escalation factors for years 3-5 (Headcount_Growth%, Salary_Escalation%, Benefit_Rate_Trend | P2-Should Have
30 | WF-ADV-06 | Data Integration Push to Reporting | User-triggered push: WFP calc module → REP WFP reporting module | Oracle Planning: EPM Automate 'Push_to_REP' job exposed via Planning form button (no BI team needed). Dept-level scope: user selects their dept, push runs for that dept only. Copy: | P1-Must Have
31 | WF-ADV-07 | Data Integration Push to FS | User-triggered push: WFP calc module → FS module for aggregation | Oracle Planning: EPM Automate 'Push_to_FS' job — user-triggered from Planning form. Dept-level: maps WFP Personnel accounts to FS Personnel accounts. CUST_WFPtoFS Groovy: validates | P1-Must Have

## Calc Rules Register
ORACLE EPM WFP — CALCULATION RULES REGISTER ¦ 53 Rules ¦ Position-Based Planning
# | Category | Rule Name | Type | Sprint | WF Refs | Calculation Logic | Dimensions | Input Source | Output Account | Notes / Edge Cases
── STANDARD ORACLE (5 rules) ──
1 | Standard Oracle | OEP_WFPCalcAll | Standard | S1 | N/A | Master WFP calculation — runs all position-based comp calcs for all entities and scenarios | All | Oracle Planning native | All WFP accounts | Must run ClearAll first to avoid double-count
2 | Standard Oracle | OEP_WFPClearAll | Standard | S1 | N/A | Clears all WFP data cube blocks before fresh recalculation | All | Oracle Planning native | All WFP accounts | Sequence: ClearAll → position calcs → AggregateAll
3 | Standard Oracle | OEP_WFPSpread | Standard | S1 | N/A | Spreads annual/periodic values to months. Modes: Even / Actual-Days / Custom_Spread | Period, Year | Oracle Planning native | All periodic accounts | Even spread default; custom for bonus/ICP payout timing
4 | Standard Oracle | OEP_WFPAggregateAll | Standard | S1 | N/A | Rolls up position → dept → division → entity for consolidated reporting | Entity, Dept | Oracle Planning native | Rollup members | Triggers after all position-level calcs complete
5 | Standard Oracle | OEP_WFPCalcByEntity | Standard | S1 | N/A | Incremental single-entity calc — real-time update without full enterprise recalc | Entity, Scenario | Oracle Planning native | Entity-scoped accounts | Used for on-demand re-calc when planner saves changes
── POSITION-BASED (2 rules) ──
6 | Position-Based | CUST_PositionLifecycle | Custom Groovy | S1 | WF-28 | Sets position status based on attributes: Filled/Unfilled/Pending/Pipeline/Closed_Attrition. Routes subsequent calcs. | Position, Period | Position attribute table | Position_Status account | Runs first in calc sequence — gates all downstream rules
7 | Position-Based | CUST_MDPlusPlanning | Custom Groovy | S1 | WF-19, WF-84 | IF Grade_Flag = MD+ THEN use actual Employee_ID salary ELSE use position-based AMS. Routes MD+ to employee-level calc. | Position, Grade, Employee | Grade dimension flag | MD_Base_Salary account | Security enforced: MD+ data restricted to HR_Admin + Finance_Admin
── BASE PAY (5 rules) ──
8 | Base Pay | CUST_AvgMonthlySalary_Filled | Custom Groovy | S3 | WF-68 | Avg_Monthly_Salary = AVG(Annual_Salary[Sub_Dept, Location, Role, Worker_Type]) / 12 for Status=Filled positions. | Position, Sub_Dept, Location, Job, Worker_Type | Talent Data Product actual salary load | AMS_Matrix assumption table | Refreshed monthly; used as base for all comp calcs
9 | Base Pay | CUST_AvgMonthlySalary_Pending | Custom Groovy | S3 | WF-69 | IF AMS_Matrix[Sub_Dept,Location,Role,Worker_Type] exists → use it. ELSE use Midpoint[Home_Location, Level] from Talent DP. | Position, Sub_Dept, Location, Job, Worker_Type | AMS_Matrix + Midpoint table | Avg_Monthly_Salary account per position | Null guard: if both null, flag position for Finance review
10 | Base Pay | CUST_ManualOverrideCalc | Custom Groovy | S4 | WF-ADV-03 | IF Override_Flag = Y THEN Effective_Salary = Override_Salary ELSE Effective_Salary = AMS_Matrix value. Cascades to all downstream calcs. | Position | Manual input form | Effective_Salary account | Override logged with requester, old and new values
11 | Base Pay | CUST_SalaryRollForward | Custom Groovy | S3 | WF-85 | Next_Year_Base = AMS_Month_12 (last month of FY incl. merit). Runs post-Final lock, pre-new-year planning open. | Position, Period, Year | Current year final AMS + Merit | Next_Year_AMS table | Ensures prior-year merit compound baked into new-year starting base
12 | Base Pay | CUST_PartialMonthCalc | Custom Groovy | S3 | WF-89 | IF Position_Status = Open AND Expected_Hire_Date set THEN Monthly_Cost[hire_month] = Full × (Days_Remaining / Days_in_Period). | Position, Period | Expected_Hire_Date attribute | Base_Salary_Partial account | All downstream calcs (merit, benefits, ICP) also prorated from hire month
── MERIT (3 rules) ──
13 | Merit | CUST_MeritEligibility | Custom Groovy | S3 | WF-83 | Merit_Eligible_Flag = Y IF Worker_Type IN (Regular_FTE, Secondment). Merit_Eligible_Flag = N IF Worker_Type IN (Intern, Contingent_Vendor, Contingent_Backfill). | Position, Worker_Type | Worker_Type dimension | Merit_Eligible_Flag attribute | Must run before CUST_MeritCalc
14 | Merit | CUST_MeritExclusion | Custom Groovy | S3 | WF-71 | IF Promotion_Flag = Y AND Promotion_Year = Current_FY THEN Merit_Pct = 0 (newly promoted excluded from merit in same year). | Position, Year | Promotion_Flag attribute | Merit_Override_Flag | Flag auto-reset to N at fiscal year start
15 | Merit | CUST_MeritCalc | Custom Groovy | S3 | WF-70 | Merit_Cost_Monthly = Avg_Monthly_Salary × Merit_Pct[Grade, Year] for Period >= Merit_Month. Zero for pre-merit months. | Position, Grade, Period | Merit_Eligible_Flag + Merit_Pct table | Merit_Cost account | Merit_Month configured per cycle; Merit_Pct table Finance-owned
── BENEFITS (1 rules) ──
16 | Benefits | CUST_BenefitsCalc | Custom Groovy | S3 | WF-72 | (Avg_Monthly_Salary + Merit_Cost_Monthly) × Blended_Benefit_Rate[Worker_Type, Location]. Includes: CPP, EI, WSIB, Group Health, Pension. | Position, Worker_Type, Location | AMS + Merit + Benefit_Rates table | Benefits_Total account | Does NOT include ICP benefits — handled by CR-22
── PROMOTIONS (1 rules) ──
17 | Promotions | CUST_PromotionCalc | Custom Groovy | S3 | WF-81 | Promotion_Cost = Avg_Monthly_Salary × Promotion_Rate[Dept, Grade]. Sets Promotion_Flag=Y. Stored separately from Base_Salary. | Position, Dept, Grade | Promotion_Rate driver (Talent DP) | Promotion_Increment account | Triggers WF-71 Merit exclusion for same-year promoted positions
── ICP (4 rules) ──
18 | ICP | CUST_ICPInYear | Custom Groovy | S3 | WF-74 | ICP_InYear_Gross = Annual_Salary × ICP_Target_Pct × Total_Fund_Multiplier × Individual_Multiplier × Dept_Multiplier. | Position, Scenario | ICP_Assumption_Form (PeopleFluent via Talent DP) | ICP_InYear_Gross account | All multipliers sourced from PeopleFluent — not manual input
19 | ICP | CUST_ICPMeritBenefits | Custom Groovy | S3 | WF-75 | ICP_Merit_Comp = (Salary + Merit) × ICP_Pct × Multiplier. ICP_Benefits = ICP_InYear_Gross × Benefit_Rate_ICP[Worker_Type]. | Position, Worker_Type | ICP_InYear_Gross + Merit | ICP_Benefits_Total account | Tracked separately from base benefits for management reporting
20 | ICP | CUST_ICPDeferred | Custom Groovy | S3 | WF-76 | Deferred_CY = ICP_InYear × Deferred_Pct. Deferred_PY_Compound = Deferred_PY_Balance × (1 + Total_Fund_RoR). Total_Deferred = CY + PY_Compounded. | Position, Year | ICP_InYear_Gross + PY Deferred balances + RoR | ICP_Deferred_CY + ICP_Deferred_PY accounts | Prior year balances carried from actuals history
21 | ICP | CUST_ICPSensitivity | Custom Groovy | S3 | WF-ADV-01 | Creates sensitivity scenarios: ICP_Sensitivity[Δ] = ICP_Base × (1 + RoR_Δ/100). Range: ±5%, ±10%, ±15%. Outputs delta table. | Position, Scenario | ICP_InYear_Gross + RoR assumption | ICP_Sensitivity_Table | Sensitivity stored in What-If scenarios, not polluting Working version
── VDIP (1 rules) ──
22 | VDIP | CUST_VDIPCalc | Custom Groovy | S3 | WF-77 | Fund_VDIP_InYear = ICP_InYear × VDIP_Pct. Compound: VDIP_Balance_t = VDIP_Balance_(t-1) × (1+Fund_RoR) + VDIP_InYear_t. Multiple vintages tracked. | Position, Year | ICP_InYear + VDIP_Pct + Fund_RoR | VDIP_2022/2023/2024 vintage accounts | Payout year: VDIP_Balance at vest date released to payout account
── LOCATION-SPECIFIC (4 rules) ──
23 | Location-Specific | CUST_HKHousingAllowance | Custom Groovy | S3 | WF-73 | IF Location=HK AND Worker_Type=Regular_FTE AND Position_Status != New_Hire THEN HK_Housing = Fixed_HK_Rate. Excludes new hires and open positions. | Position, Location, Worker_Type | HK_Rate assumption table | HK_Housing_Allowance account | Fixed rate — not salary-indexed. New hires ineligible going forward
24 | Location-Specific | CUST_BRLStatutory | Custom Groovy | S3 | WF-73 | BRL_13th_Month = BRL_Monthly_Salary (one extra month). Vacation_Bonus = BRL_Monthly_Salary × (1/3). Applied to all BRL Worker_Type = Regular_FTE. | Position, Location | BRL Monthly Salary | BRL_13th_Month + BRL_Vacation_Bonus accounts | Statutory requirement — all BRL positions must have these calculated
25 | Location-Specific | CUST_BRLStatutoryICP | Custom Groovy | S3 | WF-78 | BRL_ICP_13th = ICP_InYear / 12. BRL_ICP_Deferred_Vacation = Deferred_ICP × (1/3). Applies only to Location=BRL positions. | Position, Location | ICP_InYear_Gross + Deferred_ICP | BRL_ICP_Statutory account | Combined with CUST_BRLStatutory for total BRL statutory cost view
── FX (1 rules) ──
26 | FX | CUST_FXTranslation | Custom Groovy | S3 | WF-79 | CAD_Amount = Local_Amount × FX_Rate[Currency, FY, Annual_Avg]. Applied after all local currency calcs complete. | Position, Location, Currency | FX_Rates table (annual avg) | All account members — CAD reporting view | Local and CAD views both stored — toggle in Smart View/Dashboard
── INTERNATIONAL (1 rules) ──
27 | International | CUST_IntlAssignmentCalc | Custom Groovy | S3 | WF-90 | IF Intl_Assignment_Flag = Y AND Home_Entity ≠ Host_Entity: split cost between home/host per assignment agreement. Apply Host_Currency FX for local costs. | Position, Legal_Entity, Location | Assignment agreement table + Intl_Assignment_Flag | Home_CC_Cost + Host_CC_Cost accounts | Short-term/Long-term/Secondment assignment types have different split rules
── LOCATION-SPECIFIC (4 rules) ──
28 | Location-Specific | CUST_MumbaiCostMapping | Custom Groovy | S3 | WF-91 | Maps Mumbai-specific statutory salary/benefit components to correct Oracle accounts: PF→Benefits_Statutory, Gratuity→Benefits_LongTerm, Prof_Tax→Employer_Taxes. | Position, Location | Mumbai_Cost_Category_Mapping table | Mumbai-specific account members | Reconciles to GL account mapping for statutory reporting
── HC DRIVERS (5 rules) ──
29 | HC Drivers | CUST_VacancyCalc | Custom Groovy | S3 | WF-42 | Vacancy = Approved_HC − Filled_HC per position per period. Vacancy_Rate = Vacancy / Approved_HC. Based on position status, not flat rate. | Position, Period | Position_Status | Vacancy_HC + Vacancy_Rate accounts | WF-44: turnover applied to filled positions only, not already-vacant
30 | HC Drivers | CUST_VacancyDecomposed | Custom Groovy | S3 | WF-43 | Turnover_Vacancy_Months = Σ(days_vacant_post_departure/period_days). Pipeline_Vacancy_Months = Σ(days_unfilled_approved/period_days). Vacancy_Savings = AMS × Total_Vacancy_Months. | Position, Period | Turnover events + Hiring pipeline | Vacancy_Months_Turnover + Vacancy_Months_Pipeline + Vacancy_Savings accounts | Drill-through from total vacancy to component detail
31 | HC Drivers | CUST_TurnoverCalc | Custom Groovy | S3 | WF-44 | IF Position_Status = Filled THEN apply Turnover_Rate[Dept, Worker_Type]. IF Status = Unfilled THEN Turnover = 0. Turnover only fires on occupied seats. | Position, Dept, Worker_Type | Turnover_Rate driver table (Talent DP) | Turnover_Events account | Distinguishes turnover (replaced) vs attrition (WF-45, not replaced)
32 | HC Drivers | CUST_AttritionCalc | Custom Groovy | S4 | WF-45 | IF Attrition_Flag = Y: Position_Status → Closed_Attrition; HC decremented from effective month; cost zeroed from effective month. Position member retained for history. | Position, Period | Attrition_Flag + Effective_Attrition_Date | HC_Count + all comp accounts | Separate from Turnover — attrition = intentional non-replacement
33 | HC Drivers | CUST_DoubleOccupancyCheck | Custom Groovy | S3 | WF-50 | IF Double_Occupancy_Flag = Y: HC_Count capped at 1 for FTE metric; comp calc sums BOTH employee salaries for cost period. Supporting detail logs both Employee_IDs. | Position | Double_Occupancy_Flag attribute | HC_Count (capped) + Total_Comp (both employees) | Prevents HC overcount while correctly capturing full cost
── POSITION LIFECYCLE (4 rules) ──
34 | Position Lifecycle | CUST_TerminationLogic | Custom Groovy | S4 | WF-82 | Input: Position_ID + Effective_Term_Month. Zeroes all comp from effective month onward. Severance = Base_Salary × Sev_Weeks/52 in effective month. FTE decremented. | Position, Period | Effective_Term_Date + Severance_Policy table | Comp accounts (zeroed) + Severance account | Position status → Filled_to_Vacant; position retained in hierarchy
35 | Position Lifecycle | CUST_CCTransfer | Custom Groovy | S4 | WF-80 | Moves Employee_ID linkage from old_CC to new_CC effective from Transfer_Month. No approval gate required. HC counts updated in both CCs immediately. | Position, Entity, Dept | Transfer_Form input (old CC, new CC, effective date) | Position_CC attribute + HC_Count in both CCs | Audit log: transfer batch recorded with date, old CC, new CC, user
36 | Position Lifecycle | CUST_EffectiveDateCalc | Custom Groovy | S4 | WF-54 | Prorate cost from effective month for movements (transfer, promotion, departure). CUST_MovementAnalysis: waterfall — Opening + New + Transfers_In − Transfers_Out + Promotions − Departures = Closing. | Position, Period | Effective_Date attribute on all movements | Movement_Type accounts + HC waterfall accounts | Full movement audit trail per position per period
── VERSION CONTROL (2 rules) ──
37 | Version Control | CUST_VersionLock | Custom Groovy | S1 | WF-02 | Checks Version_Status before allowing write. IF Status = Approved OR Status = Final THEN reject write; prompt for change request. Top-of-house approval required to unlock. | Version | Version_Status attribute | Version_Status account | Enforced on all Groovy rule writes and form submissions
38 | Version Control | CUST_VersionPromotion | Custom Groovy | S1 | WF-41 | Copies Working version data to Draft or Final on promotion event. Enforces stage progression: Baseline→Working→Draft→Final. Logs promotion with timestamp and approver. | Version, All | Working version data | Target version (Draft/Final) | What-If to permanent: CUST_WhatIfPromote copies selected WhatIf to named version
── DATA QUALITY (2 rules) ──
39 | Data Quality | CUST_DataValidation | Custom Groovy | S2 | WF-11, WF-16 | Post-load integrity check: validates CC_Location_Matrix, Job_Grade_Workday_Match, Position_Employee_Link. Flags invalid combos. All-or-nothing: if P1 errors found, marks load as failed. | All loaded dimensions | EPM DM load output | Validation_Status + Error_Log accounts | Error report auto-generated and emailed to Data_Ops team
40 | Data Quality | CUST_DataSourceTag | Custom Groovy | S2 | WF-14 | Tags each loaded data cell with Data_Source: Workday / PeopleFluent / Talent_DP / GL_ERP / Manual. Manual overrides flagged distinctly. | All | Load job metadata | Data_Source attribute on all accounts | Enables traceability reports showing source breakdown by account
── REPORTING (7 rules) ──
41 | Reporting | CUST_AvgSalaryByMatrix | Custom Groovy | S2 | WF-65 | Computes AVG(Annual_Salary) by [Sub_Dept, Location, Role, Grade] from Talent DP actual salary load. Consolidated at Role level. Stored to AMS_Matrix assumption table. | Sub_Dept, Location, Job, Grade | Talent Data Product actual salary | AMS_Matrix table (used by CR-08/09) | Monthly refresh; used as basis for all base pay calcs
42 | Reporting | CUST_WFPtoREP | Custom Groovy | S4 | WF-ADV-06, WF-95 | Copies approved WFP version to Reporting (REP WFP) cube. User-triggered: no BI team required. Dept-level scope: user selects dept, push runs for that dept only. | All | Approved WFP version data | REP WFP cube target | Confirmation report generated post-push; audit log: timestamp, user, dept, version
43 | Reporting | CUST_WFPtoFS | Custom Groovy | S4 | WF-ADV-07 | Maps WFP Personnel accounts to FS module accounts. Validates WFP_Total = FS_Personnel_Total (WF-53) before write. User-triggered by dept. Reconciliation report auto-generated. | Personnel accounts, CC, Period | Approved WFP version | FS module Personnel_Total accounts | Push blocked if reconciliation fails — error displayed to user
44 | Reporting | CUST_HierarchyReconcile | Custom Groovy | S4 | WF-32 | Validates Financial_View_Total = Management_View_Total per period per entity. Flags rounding or mapping gaps > $1K. | Account, Entity, Period | Both hierarchy views | Reconciliation_Gap account | Nightly job; alert if gap found; blocks NR report generation until resolved
45 | Reporting | CUST_WFPtoFSReconcile | Custom Groovy | S4 | WF-53 | Compares Personnel_Total in WFP cube vs FS cube. Outputs: WFP_Total, FS_Total, Difference, Tolerance_Flag (flag if > $5K or > 0.1%). | Personnel accounts, Period | WFP cube + FS cube | Reconcile_Variance account | Nightly automated check; dashboard tile: RAG status; escalation if P1 gap
46 | Reporting | CUST_AuditReport | Custom Groovy | S4 | WF-03 | Compares Version_A vs Version_B at cell level, outputs delta with cell address, old value, new value, commentary if available. Used for period-over-period and version comparison. | All | Two specified versions | Audit_Delta_Export (CSV) | Weekly export to SharePoint for compliance; on-demand for ad-hoc audit requests
47 | Reporting | CUST_MgmtReportClassify | Custom Groovy | S4 | WF-04 | Routes account members to Management_View hierarchy: Personnel / G&A / ICP / Other. Separate from GL hierarchy. Validates Management_Total = Financial_Total. | Account | Account hierarchy | Management_View_Account members | No changes to GL accounts — management classification is alternate rollup only
── SCENARIOS (3 rules) ──
48 | Scenarios | CUST_BaselineRefresh | Custom Groovy | S2 | WF-49 | Copies latest available Forecast version to Baseline version. Checks: Q3 available? Use Q3. Otherwise Q2. Governance: requires PMO approval before execution. | All | Latest Forecast version | Baseline version | Lock: Baseline locked once Annual Budget cycle opens — no further refresh
49 | Scenarios | CUST_BaselineLock | Custom Groovy | S2 | WF-88 | IF Version=Baseline AND Baseline_Lock_Flag=Y THEN reject EPM DM write AND reject all Business Rule writes to Baseline version. | Version, All | Baseline_Lock_Flag | N/A (enforcement rule) | Prevents auto-refresh from overwriting planning baseline mid-cycle
50 | Scenarios | CUST_VersionLifecycle | Custom Groovy | S1 | WF-22, WF-27 | Enforces version stage: What-If cannot promote to Enterprise without Finance_Admin approval. End-of-cycle: archives What-If versions. Max 5 concurrent What-If versions enforced. | Version | Version_Status + Version_Type (Enterprise/WhatIf) | Version lifecycle log | Annual EPM Automate cleanup job deletes archived What-If versions
── MASS UPDATES (1 rules) ──
51 | Mass Updates | CUST_MassUpdate | Custom Groovy | S4 | WF-ADV-02 | Accepts array of position IDs with bulk field updates (CC, grade, worker type, start/end date, role). Single EPM rule invocation updates all selected rows. Audit: batch transaction record. | Position, multiple dims | Mass_Change_Form multi-row input | All affected position attributes | Validation: each position checked individually; partial failures rolled back for that position
── SENSITIVITY (1 rules) ──
52 | Sensitivity | CUST_ScenarioVariance | Custom Groovy | S4 | WF-40, WF-94 | Budget vs Forecast vs Actual: $ variance, % variance, FTE variance. Materiality threshold flag: > configurable $ or % threshold triggers commentary prompt. | Scenario, Period, Dept | Budget + Forecast + Actual versions | Variance_$ + Variance_% + FTE_Variance accounts | Threshold configurable by Finance; flags shown in dashboard RAG tiles
── POSITION LIFECYCLE (4 rules) ──
53 | Position Lifecycle | CUST_RetirementCalc | Custom Groovy | S4 | WF-92 | Full-year cost reserved until effective retirement date then zeroed. CUST_VDIPDeferral: moves deferred ICP/VDIP to Central_CC post-retirement. Retirement_Flag on position. | Position, Period | Retirement_Flag + Retirement_Date | Retirement_Reserved_Cost + Central_CC VDIP accounts | Position member retained for history; CC reallocation tracked in audit log

## Position-Based Planning Design
POSITION-BASED PLANNING — ARCHITECTURE DESIGN ¦ Below MD: Position-Based ¦ MD+: Employee-Based
1. PLANNING MODEL — POSITION vs EMPLOYEE
Component | Design Detail | Owner | WF Reference
Planning Approach — Below MD | Position-Based Planning: all staff below MD level planned at Position_ID granularity. Employee_ID linked to position as attribute. Salary = AMS from Talent DP matrix, not individual actual. | Finance / HR | WF-19
Planning Approach — MD and Above | Employee-Based Planning: MD+ roles planned at individual Employee_ID with actual salary. Grade_Flag='MD+' routes to CUST_MDPlusPlanning. Restricted access: HR_Admin + Finance_Admin only. | HR_Admin / CFO | WF-84
Position Status Lifecycle | Filled → Unfilled → Pending_Hire → Pipeline → Closed_Attrition. CUST_PositionLifecycle gates all downstream calc rules based on current status. | PwC / HR | WF-28
Position Hierarchy Design | Position_ID (sparse dimension). Grouped by: Entity → Dept → Job_Family → Job_Code → Grade. Position member naming: {CC}_{JobCode}_{Seq} (e.g., CORP-FIN_FAAN_001). | PwC | WF-19, WF-20
Worker Type Dimension | Separate dimension: Regular_FTE ¦ Intern ¦ Secondment ¦ Contingent_Vendor ¦ Contingent_Backfill. Drives: merit eligibility, benefit rates, ICP eligibility, reporting splits. | PwC | WF-29
Position-Employee Linkage | Employee_ID stored as position attribute. Authorized users can drill position → employee. Anonymity threshold: suppress detail if CC headcount < 3. | IT / HR | WF-64, WF-61
Contingent Workforce | Linked to position (backfill) or position-less (project/pool). CUST_ContractorCost: Bill_Rate × Hours × Utilization%. Time-bound: start/end dates required. | Finance | WF-34, WF-47, WF-48
Double Occupancy | Double_Occupancy_Flag on position. HC_Count capped at 1; cost captures both employees. Used for maternity leave cover, shadowing, handover periods. | HR | WF-50
Pipeline / Proposed Positions | Position_Status = Pipeline. CUST_PipelinePosition: partial-year cost from proposed hire date. Auto-match when Workday creates position: status promoted to Filled. | HR / Finance | WF-37
Transfer Between Cost Centres | CUST_CCTransfer: direct move, no approval gate. Employee linkage and HC counts updated immediately in both CCs. Full audit log. | Finance | WF-80
Retirement Planning | Full-year cost reserved until effective retirement date. Deferred/VDIP costs moved to Central_CC. Position retained for historical audit trail. | Finance / HR | WF-92
2. CALC RULE SEQUENCE — POSITION-BASED PLANNING
Step | Calc Rule | Logic Summary | Dependency
1. Position Status | CUST_PositionLifecycle | Sets Filled/Unfilled/Pipeline/Attrition status — gates all downstream calcs | Must run first
2. MD+ Routing | CUST_MDPlusPlanning | Routes MD+ to employee-level actual salary; below-MD to AMS matrix | Requires Grade_Flag
3. AMS — Filled | CUST_AvgMonthlySalary_Filled | AVG(Annual_Salary[SubDept,Loc,Role,WorkerType]) / 12 for filled positions | Talent DP load complete
4. AMS — Pending | CUST_AvgMonthlySalary_Pending | AMS from matrix or midpoint fallback for new/pipeline positions | AMS_Matrix + Midpoint loaded
5. Manual Override | CUST_ManualOverrideCalc | IF Override_Flag=Y: use Override_Salary for all downstream calcs | Override form input
6. Partial Month | CUST_PartialMonthCalc | Prorate hire-month cost by Expected_Hire_Date | Expected_Hire_Date set
7. Salary Roll-Forward | CUST_SalaryRollForward | Last-month AMS+Merit → next year base (runs post-Final lock) | Prior year Final locked
8. Merit Eligibility | CUST_MeritEligibility | Flag eligible worker types (Regular_FTE, Secondment) | Worker_Type dimension
9. Merit Exclusion | CUST_MeritExclusion | Zero merit for newly promoted positions in same year | Promotion_Flag set
10. Merit Calc | CUST_MeritCalc | AMS × Merit_Pct[Grade] from Merit_Month onward | Merit eligibility flags
11. Benefits | CUST_BenefitsCalc | (AMS + Merit) × Blended_Benefit_Rate[Worker_Type, Location] | AMS + Merit complete
12. Promotions | CUST_PromotionCalc | AMS × Promotion_Rate — stored separately; sets Promotion_Flag | Promotion_Rate from Talent DP
13. ICP In-Year | CUST_ICPInYear | Annual_Salary × ICP_Target × Fund_Mult × Indiv_Mult | PeopleFluent ICP assumptions loaded
14. ICP Merit/Benefits | CUST_ICPMeritBenefits | ICP on merit-adjusted salary + ICP benefits component | CUST_ICPInYear complete
15. ICP Deferred | CUST_ICPDeferred | CY deferred + PY compound at Fund_RoR | Prior-year deferred balances
16. VDIP | CUST_VDIPCalc | Fund + PI VDIP with compounding to payout year | ICP calcs complete
17. Location: HK Housing | CUST_HKHousingAllowance | Fixed HK rate for existing Regular_FTE in HK (not new hires) | Location=HK filter
18. Location: BRL Statutory | CUST_BRLStatutory | 13th month + vacation bonus for all BRL positions | Location=BRL filter
19. Location: BRL ICP | CUST_BRLStatutoryICP | BRL statutory ICP components | ICP calcs + Location=BRL
20. Mumbai Mapping | CUST_MumbaiCostMapping | PF, Gratuity, Prof_Tax → correct Oracle accounts | Location=Mumbai filter
21. Intl Assignment | CUST_IntlAssignmentCalc | Host/home cost split + host currency FX for expats | Intl_Assignment_Flag
22. FX Translation | CUST_FXTranslation | Local → CAD at annual average rate (runs last) | All local-currency calcs complete
23. Vacancy Calc | CUST_VacancyCalc | Approved_HC − Filled_HC per position per period | Position_Status values
24. Vacancy Decomposed | CUST_VacancyDecomposed | Turnover vacancy months + pipeline vacancy months → savings | Turnover events loaded
25. Aggregate | OEP_WFPAggregateAll | Position → Dept → Division → Entity rollup | All position calcs complete
26. FX Translation | OEP_WFPSpread | Spread annual values to monthly periods | AggregateAll complete
3. DATA FLOW — SOURCE SYSTEMS TO EPM WFP
Source System | Data Payload | EPM Target | Frequency / Method
Workday → Talent Data Product | Position_ID, Employee_ID, OrgUnit, JobCode, Grade, Worker_Type, Effective_Date, Position_Status | Position dimension + Employee attribute + Job/Grade dimensions | Monthly snapshot via Talent Data Product API. SOR: Workday (WF-10)
Talent Data Product → EPM DM | Actual salary by position, AMS by [SubDept, Location, Role, Grade], Midpoint by [Home_Location, Level] | AMS_Matrix + Midpoint assumption tables | Monthly load (WF-65, WF-66). Delta refresh available (WF-12)
PeopleFluent → Talent Data Product → EPM | ICP_Target_Pct, In_Year_ICP_Pct, Deferred_Pct, Fund_Multiplier, Individual_Multiplier, Total_Fund_RoR, PI_RoR, VDIP_Pct | ICP_Assumption_Form + ICP_Rates table | Monthly sync. Quarterly cycle snapshot (WF-15, WF-67)
GL / ERP → EPM Data Management | Actuals by account, cost centre, period | Actuals scenario — all account members | Nightly load via EPM Automate. Locked at period close (WF-10)
Data Fabric / Oracle Financials → EPM | CC Hierarchy, Account Hierarchy, GL account mapping | Dimension hierarchy + Management alternate hierarchy | Nightly delta sync (WF-ADV-04). LCM snapshot before each sync
FX Rate Feed → EPM | Annual average FX rates by currency and fiscal year | FX_Rates[Currency, FY, Annual_Avg] assumption table | Annual load at budget cycle open; updated if rates change (WF-79)
Manual Inputs (Finance / HR) | Driver overrides: Merit%, COLA%, Benefit_Rate, Turnover_Rate. Manual salary overrides (WF-ADV-03). Commentary (WF-35, WF-36) | Driver assumption forms + Override cells + Cell text | During planning windows. All overrides logged with requester and reason

## Sprint Deliverables
SPRINT DELIVERABLES REGISTER ¦ Oracle EPM WFP Release 1a ¦ All Sprints
Del ID | Sprint | Deliverable | Owner | Due | Accepts
DEL-DA-01 | Design & Align | Requirements Traceability Matrix (RTM) — all 97+ WF requirements mapped | PwC | 28-Feb | Sponsor / CFO
DEL-DA-02 | Design & Align | Position-Based Planning Architecture Document — design patterns, PBP vs Employee-based rules | PwC | 28-Feb | Finance / IT
DEL-DA-03 | Design & Align | Dimension Design Specification — all 7+ dimensions including Location, Worker_Type, Project | PwC | 28-Feb | PwC PMO
DEL-DA-04 | Design & Align | Key Design Decisions Log — 30+ KDDs (PBP approach, MD+ threshold, ICP treatment, BOR design) | PwC / Sponsor | 28-Feb | Sponsor
DEL-DA-05 | Design & Align | Future-State Architecture — WFP module + OPEX G&A + ICP/VDIP layer | PwC | 28-Feb | Finance / IT
DEL-DA-06 | Design & Align | Configuration Workbook v1.0 — dimension register, metadata specs, calc rule specs | PwC | 28-Feb | Sponsor
DEL-DA-07 | Design & Align | Integration Architecture — Workday/PeopleFluent/Talent DP/GL/FX to EPM | PwC / IT | 28-Feb | IT
DEL-DA-08 | Design & Align | Security Design Document — 5 job roles, DAFs, MD+ restrictions, anonymity thresholds | PwC / IT Sec | 28-Feb | IT Sec
DEL-DA-09 | Design & Align | Calc Rules Specification — all 53 rules with formula logic and sequence | PwC | 28-Feb | Finance
DEL-DA-10 | Design & Align | 3-Year Planning Calendar + Version Lifecycle Framework | PwC / Finance | 28-Feb | CFO
DEL-POC-01 | POC | POC Findings Report — validated AMS calc, ICP Groovy, position-based model on rep data | PwC | 28-Feb | Finance / IT
DEL-S1-01 | S1 | 5 Standard Oracle WFP Rules deployed to DEV (CalcAll, ClearAll, Spread, AggregateAll, CalcByEntity) | PwC | 28-Mar | Finance
DEL-S1-02 | S1 | Version dimension — 5 Enterprise + 5 What-If members built and governed (WF-27, WF-22) | PwC | 28-Mar | PMO
DEL-S1-03 | S1 | CUST_VersionLock + CUST_VersionPromotion + CUST_VersionLifecycle deployed (WF-02, WF-41, WF-22) | PwC | 28-Mar | Finance
DEL-S1-04 | S1 | Position dimension — 500+ active positions loaded; Position_Status lifecycle attributes set (WF-28) | PwC / HR | 28-Mar | HR
DEL-S1-05 | S1 | CUST_PositionLifecycle + CUST_MDPlusPlanning deployed and unit tested (WF-19, WF-84, WF-28) | PwC | 28-Mar | Finance
DEL-S1-06 | S1 | Security: 5 job roles + all DAFs (Account, CC, Job, Employee, Version) configured (WF-58–64) | IT Sec / PwC | 28-Mar | IT Sec
DEL-S1-07 | S1 | Multi-currency setup: all currencies + FX_Rates table + CAD reporting currency (WF-25, WF-79) | PwC / IT | 28-Mar | Finance
DEL-S1-08 | S1 | Worker_Type dimension + Location dimension built and loaded (WF-21, WF-29) | PwC | 28-Mar | PwC PMO
DEL-S2-01 | S2 | Workday → Talent DP → EPM DM position load live: HRIS_Position_Snapshot_Monthly (WF-10) | IT / PwC | 25-Apr | IT
DEL-S2-02 | S2 | PeopleFluent → Talent DP → ICP_Assumptions_Load live + ICP_Rates table populated (WF-15, WF-67) | IT / PwC | 25-Apr | IT
DEL-S2-03 | S2 | CUST_DataValidation + CUST_DataSourceTag deployed: error reporting + source traceability (WF-11,14,16) | PwC | 25-Apr | Finance
DEL-S2-04 | S2 | GL Actuals load live; 3yr historical + FY25 B/F loaded and reconciled (WF-08, WF-09) | IT / Finance | 25-Apr | Finance
DEL-S2-05 | S2 | Midpoint_Load + CUST_AvgSalaryByMatrix + AMS_Matrix assumption table built (WF-65, WF-66) | PwC / IT | 25-Apr | Finance
DEL-S2-06 | S2 | CUST_BaselineRefresh + CUST_BaselineLock deployed (WF-49, WF-88) | PwC | 25-Apr | PMO
DEL-S2-07 | S2 | Hierarchy_Sync_Load: Oracle Financials CC + Account hierarchy nightly sync (WF-ADV-04) | IT / PwC | 25-Apr | IT
DEL-S2-08 | S2 | EPM Automate: all nightly jobs scheduled (load → calc → export → reconcile) (WF-17, WF-12) | IT | 25-Apr | IT
DEL-S3-01 | S3 | All 26 position-based compensation Groovy rules deployed and unit tested (CR-07 through CR-32) | PwC | 30-May | Finance / HR
DEL-S3-02 | S3 | ICP Suite: CUST_ICPInYear + ICPMeritBenefits + ICPDeferred + VDIPCalc + ICPSensitivity (WF-74–77) | PwC | 30-May | Finance
DEL-S3-03 | S3 | Location rules: HK Housing, BRL Statutory (×2), Mumbai Mapping, Intl Assignment (WF-73,78,90,91) | PwC | 30-May | Finance
DEL-S3-04 | S3 | FX Translation: CUST_FXTranslation live across all location/currency combos (WF-79) | PwC | 30-May | Finance
DEL-S3-05 | S3 | HC Driver rules: Vacancy, VacancyDecomposed, TurnoverCalc, DoubleOccupancy (WF-42–44, WF-50) | PwC | 30-May | Finance
DEL-S3-06 | S3 | S3 Playback — live calc demo: position → AMS → Merit → Benefits → ICP → VDIP → FX chain | PMO / Finance | 30-May | Finance / CFO
DEL-S4-01 | S4 | All 27 remaining Groovy rules deployed: lifecycle, reporting, scenarios, mass update (CR-33 to CR-53) | PwC | 27-Jun | Finance
DEL-S4-02 | S4 | All planning forms: Position Planning, New Hire, OPEX G&A, Mass Change, Contingent, Transfer | PwC | 27-Jun | Finance
DEL-S4-03 | S4 | Management dashboards: HC summary, FTE gap, OPEX variance, BOR/ICP, Scenario comparison | PwC | 27-Jun | Finance / CFO
DEL-S4-04 | S4 | Narrative Reporting templates: WFP Mgmt Report, BOR Report, Audit Report, Variance Report (WF-87, WF-03, WF-96) | PwC / Finance | 27-Jun | CFO
DEL-S4-05 | S4 | Push to Reporting (WFP→REP) + Push to FS module — user-triggered, dept-scoped (WF-ADV-06, WF-ADV-07) | PwC / IT | 27-Jun | Finance
DEL-S4-06 | S4 | SIT test scripts — 120+ test cases mapped to all 97 WF requirements and 53 calc rules | PwC | 27-Jun | PMO
DEL-SIT-01 | SIT | SIT Execution Report — all 120+ scripts, defect log, regression sign-off | PwC PMO | 18-Jul | PMO / Sponsor
DEL-UAT-01 | UAT | UAT Execution Report — 60+ business scenarios, all WF acceptance criteria met | Finance / CFO | 01-Aug | CFO / Sponsor
DEL-GO-01 | Go-Live | Go-Live Package: cutover plan, PROD data reconciliation, training completion, Go/No-Go sign-off | PwC / Finance | 20-Aug | CIO / CFO / Sponsor