## Project Plan
ORACLE EPM CLOUD — WORKFORCE PLANNING & OPEX G&A ¦ RELEASE 1a DELIVERY PLAN ¦ 2025
✏ Start / End dates in columns D & E are EDITABLE (shown in blue) — Gantt bars update automatically ¦ ▲ = Milestone Gate ¦ ▼ = TODAY marker
DELIVERY PHASES | [6 empty] | Design & Align | POC |  |  | Build S1-S4 | [7 empty] | SIT | UAT |  | Go-Live | Parallel Run |  |  |  | Evolve
Phases, Workstreams & Tasks | [6 empty] | 2025
[7 empty] | Jan |  | Feb |  | Mar |  |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  |  | Oct |  | Nov
↳ period-start dates (formula reference) | [6 empty] | 2025-01-06 | 2025-01-20 | 2025-02-03 | 2025-02-17 | 2025-03-03 | 2025-03-17 | 2025-03-31 | 2025-04-14 | 2025-04-28 | 2025-05-12 | 2025-05-26 | 2025-06-09 | 2025-06-23 | 2025-07-07 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-09-01 | 2025-09-15 | 2025-09-29 | 2025-10-13 | 2025-10-27 | 2025-11-10
# | Phase / Workstream / Task | Owner / DRI | Start | End | Duration | Status
FY27 BUSINESS PLANNING CYCLE — PARALLEL TRACK (Current System)
1 | Annual planning — current system config, data clean-up & optimization | Finance / IT | 2025-01-06 | 2025-12-31 |  | Active
2 | Planning Guidance Playbook & System Preparation | Mgr. FP&A | 2025-06-02 | 2025-09-26 |  | Planned
3 | Dept. Budget Submissions | Dept. Finance Leads | 2025-10-01 | 2025-10-31 |  | Planned
4 | Reviews, Iterations & Consolidation | CFO / FP&A | 2025-11-03 | 2025-12-19 |  | Planned
RELEASE 1a — ORACLE EPM WFP (Workforce Planning) & OPEX: G&A Expenses (FS)
| PHASE 1 — DESIGN & ALIGN (January – February) | PwC / Finance | 2025-01-06 | 2025-02-28 |  | Complete
5 | 1.1 Program Governance & Mobilization | PwC PMO | 2025-01-06 | 2025-01-17 |  | Complete
6 | Project charter, scope baseline & RACI matrix | PwC PMO / Sponsor | 2025-01-06 | 2025-01-10 |  | Complete
7 | Program governance framework — SteerCo, workstream cadence | PwC PMO | 2025-01-06 | 2025-01-10 |  | Complete
8 | Risk & issue register (RAID log) setup | PwC PMO | 2025-01-06 | 2025-01-10 |  | Complete
9 | Instance Management Strategy — DEV / TEST / UAT / PROD | PwC / IT | 2025-01-13 | 2025-01-17 |  | Complete
10 | Change control process & baseline freeze protocol | PwC PMO | 2025-01-13 | 2025-01-17 |  | Complete
11 | 1.2 Stakeholder Discovery & Current-State Assessment | PwC | 2025-01-13 | 2025-02-07 |  | Complete
12 | CFO / FP&A discovery — planning process, pain points, success criteria | PwC | 2025-01-13 | 2025-01-17 |  | Complete
13 | HR / HRBP discovery — position master, org structure, HRIS data quality | PwC | 2025-01-13 | 2025-01-17 |  | Complete
14 | IT / Architecture discovery — integration landscape, data volumes, security | PwC | 2025-01-20 | 2025-01-24 |  | Complete
15 | Dept. Finance leads — budget process, OPEX cost drivers, reporting needs | PwC | 2025-01-20 | 2025-01-31 |  | Complete
16 | As-is process maps — WFP, headcount budgeting, OPEX planning | PwC | 2025-01-27 | 2025-02-07 |  | Complete
17 | Legacy tool / spreadsheet inventory & gap analysis | PwC | 2025-01-27 | 2025-02-07 |  | Complete
18 | Data quality assessment — position, compensation, org hierarchy | PwC / IT | 2025-01-27 | 2025-02-07 |  | Complete
19 | 1.3 Requirements & Future-State Architecture | PwC | 2025-01-27 | 2025-02-21 |  | Complete
20 | Requirements Traceability Matrix (RTM) — WFP & OPEX G&A | PwC | 2025-01-27 | 2025-02-07 |  | Complete
21 | Future-State Architecture document — WFP module design | PwC | 2025-02-03 | 2025-02-14 |  | Complete
22 | Future-State Architecture document — OPEX G&A (FS) module | PwC / Finance | 2025-02-03 | 2025-02-14 |  | Complete
23 | Key Design Decisions (KDD) log — 25+ decisions captured & signed off | PwC / Sponsor | 2025-02-03 | 2025-02-14 |  | Complete
24 | RICE prioritization — backlog scoring (Reach, Impact, Confidence, Effort) | PwC PMO | 2025-02-10 | 2025-02-14 |  | Complete
25 | Configuration Workbook — dimension register, metadata specs | PwC | 2025-02-10 | 2025-02-21 |  | Complete
26 | BOR / ICP framework design — below-the-line ICP, allocation keys | PwC / CFO | 2025-02-10 | 2025-02-21 |  | Complete
27 | Integration architecture design — HRIS→EPM, ERP GL→EPM, EPM Automate | PwC / IT | 2025-02-10 | 2025-02-21 |  | Complete
28 | Security & access design — job roles, data access filters, SSO | PwC / IT Sec | 2025-02-17 | 2025-02-21 |  | Complete
29 | Calculation rules specification — 20 rules (5 standard + 15 Groovy) | PwC | 2025-02-17 | 2025-02-21 |  | Complete
▲ | ▲ DESIGN GATE — KDDs, RTM, Architecture & Config Workbook signed off | Sponsor / CFO | 2025-02-28 | 2025-02-28 |  | Complete
| PHASE 2 — PROOF OF CONCEPT (Late January – February, overlaid with Design) | PwC | 2025-01-27 | 2025-02-28 |  | Complete
30 | 2.1 POC Environment Setup | PwC / IT | 2025-01-27 | 2025-01-31 |  | Complete
31 | Oracle PBCS WFP sandbox provisioning (isolated POC instance) | IT | 2025-01-27 | 2025-01-31 |  | Complete
32 | Representative data extract — 50–100 positions, 2-yr actuals sample | PwC / HR | 2025-01-27 | 2025-01-31 |  | Complete
33 | 2.2 POC Build & Validation | PwC | 2025-02-03 | 2025-02-21 |  | Complete
34 | Core WFP dimension scaffold (Entity, Dept, Job Code, Scenario) | PwC | 2025-02-03 | 2025-02-07 |  | Complete
35 | Standard calc rules run (OEP_WFPCalcAll, WFPSpread) on sample data | PwC | 2025-02-03 | 2025-02-07 |  | Complete
36 | Prototype Groovy: salary escalation & benefits loading on sample positions | PwC | 2025-02-10 | 2025-02-14 |  | Complete
37 | Driver & assumption table validation (Merit%, COLA%, Benefit_Rates[]) | PwC / Finance | 2025-02-10 | 2025-02-14 |  | Complete
38 | OPEX G&A driver prototype — headcount-linked T&E, IT, Facilities | PwC | 2025-02-10 | 2025-02-14 |  | Complete
39 | BOR/ICP below-the-line split — prototype validation with Finance | PwC / Finance | 2025-02-17 | 2025-02-21 |  | Complete
40 | Performance test — calc run time on representative data volume | PwC | 2025-02-17 | 2025-02-21 |  | Complete
41 | 2.3 POC Findings & Design Confirmation | PwC / Finance | 2025-02-24 | 2025-02-28 |  | Complete
42 | POC findings report — validated assumptions, open issues, design changes | PwC | 2025-02-24 | 2025-02-28 |  | Complete
43 | Design updates from POC findings — incorporated into Config Workbook | PwC | 2025-02-24 | 2025-02-28 |  | Complete
44 | POC sign-off — Finance & IT confirm design is fit for Build | Finance / IT | 2025-02-28 | 2025-02-28 |  | Complete
| PHASE 3 — BUILD: AGILE SPRINTS 1–4 (March – June) | PwC | 2025-03-03 | 2025-06-27 |  | In Progress
45 | SPRINT 1 — Core Application & Environment Setup (Mar 3 – Mar 28) | PwC / IT | 2025-03-03 | 2025-03-28 |  | In Progress
46 | Oracle PBCS WFP module provisioning — DEV / TEST / UAT / PROD environments | IT | 2025-03-03 | 2025-03-07 |  | In Progress
47 | SSO & identity provisioning (Azure AD / Okta); MFA enforcement | IT Security | 2025-03-03 | 2025-03-07 |  | In Progress
48 | Security roles build — Planner, Reviewer, Admin, Read-Only (DEV) | IT / PwC | 2025-03-10 | 2025-03-14 |  | In Progress
49 | Full metadata load — all 7 dimensions & hierarchies (DEV) | PwC | 2025-03-10 | 2025-03-21 |  | In Progress
50 | Application settings — planning unit hierarchy, approval workflow config | PwC | 2025-03-17 | 2025-03-21 |  | Planned
51 | Position master build — 500+ active & proposed positions loaded | PwC / HR | 2025-03-17 | 2025-03-28 |  | Planned
52 | Standard Oracle WFP calc rules deployed: OEP_WFPCalcAll, WFPClearAll, WFPSpread, WFPAggregateAll, WFPCalcByEntity | PwC | 2025-03-17 | 2025-03-28 |  | Planned
53 | Data conversion: initial position & org hierarchy load from HRIS (DEV) | PwC / IT | 2025-03-24 | 2025-03-28 |  | Planned
54 | Sprint 1 Playback — environment demo; metadata validation; std calc rules | PMO / Finance | 2025-03-28 | 2025-03-28 |  | Planned
55 | SPRINT 2 — Baseline Workflows & Integrations (Mar 31 – Apr 25) | PwC / IT | 2025-03-31 | 2025-04-25 |  | Planned
56 | Planning unit hierarchy — dept-level budget ownership & approval routing | PwC / Finance | 2025-03-31 | 2025-04-04 |  | Planned
57 | Scenario / Version strategy — Budget, Forecast Q1–Q3, Plan, Actual | PwC | 2025-03-31 | 2025-04-04 |  | Planned
58 | Planning calendar configuration — submission windows, lock/unlock cycles | PwC / Finance | 2025-04-07 | 2025-04-11 |  | Planned
59 | HRIS (Workday) → Oracle EPM integration — position/employee extract build | IT / PwC | 2025-04-07 | 2025-04-18 |  | Planned
60 | GL Actuals (ERP) → EPM integration via EPM Data Management | IT / PwC | 2025-04-07 | 2025-04-18 |  | Planned
61 | EPM Automate — nightly data load scheduler build & testing | IT | 2025-04-14 | 2025-04-18 |  | Planned
62 | Data conversion: GL actuals (3 yrs) & FY25 Budget/Forecast load to DEV | PwC / IT | 2025-04-14 | 2025-04-25 |  | Planned
63 | Integration smoke testing — end-to-end data flow validation | PwC / IT | 2025-04-21 | 2025-04-25 |  | Planned
64 | Sprint 2 Playback — integration demo; historical data in DEV; workflow walkthrough | PMO / Finance | 2025-04-25 | 2025-04-25 |  | Planned
65 | SPRINT 3 — Workforce Logic, Calculations & Automation (Apr 28 – May 30) | PwC | 2025-04-28 | 2025-05-30 |  | Planned
66 | CUST_SalaryEscalation: Merit % by Job Grade & Seniority; roll-forward from actuals | PwC | 2025-04-28 | 2025-05-09 |  | Planned
67 | CUST_COLAAdjustment: CPI-linked COLA; unionized vs non-unionized treatment | PwC | 2025-04-28 | 2025-05-09 |  | Planned
68 | CUST_BonusCalc: STI = Base × Bonus_Target_Pct × Perf_Modifier (scenario-driven) | PwC | 2025-05-05 | 2025-05-16 |  | Planned
69 | CUST_BenefitsLoading: CPP, EI, WSIB, Group Benefits, Pension match (FT vs PT) | PwC | 2025-05-05 | 2025-05-16 |  | Planned
70 | CUST_VacancyRate & CUST_FTEGapAnalysis: approved vs filled; gap threshold flag | PwC | 2025-05-12 | 2025-05-23 |  | Planned
71 | CUST_NewHireRamp: partial-year cost = Annual × (Remaining_Mo/12) × Ramp% | PwC | 2025-05-12 | 2025-05-23 |  | Planned
72 | CUST_TerminationLogic: zero comp from term date; severance loading rule | PwC | 2025-05-19 | 2025-05-30 |  | Planned
73 | Assumption table build: Merit_Pct[Grade,Year], COLA%, Benefit_Rates[], Ramp schedules | PwC / Finance | 2025-04-28 | 2025-05-30 |  | Planned
74 | Compensation calc rule unit testing — 50-position validation suite | PwC | 2025-05-26 | 2025-05-30 |  | Planned
75 | Sprint 3 Playback — live Groovy calc demo; end-to-end comp calc walkthrough | PMO / Finance / HR | 2025-05-30 | 2025-05-30 |  | Planned
76 | SPRINT 4 — Data, Reporting, Security & SIT Readiness (Jun 2 – Jun 27) | PwC | 2025-06-02 | 2025-06-27 |  | Planned
77 | CUST_ContractorCost, CUST_OPEXDriverCalc, CUST_HCtoOPEXLink (Sprint 4 rules) | PwC | 2025-06-02 | 2025-06-13 |  | Planned
78 | CUST_ICPSpread & CUST_BORAllocation — below-the-line ICP & pool allocation | PwC | 2025-06-02 | 2025-06-13 |  | Planned
79 | CUST_ScenarioVariance: Budget vs Forecast vs Actual ($ var, % var, FTE var) | PwC | 2025-06-09 | 2025-06-20 |  | Planned
80 | All input forms — Position planning, New Hire/Attrition, OPEX G&A by cost centre | PwC | 2025-06-02 | 2025-06-20 |  | Planned
81 | Management dashboards — HC summary, OPEX view, FTE gap alerts, variance tiles | PwC | 2025-06-09 | 2025-06-20 |  | Planned
82 | Narrative Reporting — WFP Management Report template (Oracle NR) | PwC / Finance | 2025-06-16 | 2025-06-27 |  | Planned
83 | Security role hardening — final role-based access validation (TEST env) | IT Sec / PwC | 2025-06-09 | 2025-06-13 |  | Planned
84 | Data conversion: full TEST environment load — positions, 3yr actuals, FY25 data | PwC / IT | 2025-06-16 | 2025-06-27 |  | Planned
85 | SIT test scripts preparation — 120+ test cases mapped to RTM | PwC | 2025-06-16 | 2025-06-27 |  | Planned
86 | SIT entry criteria review — environment readiness, defect log baseline | PwC PMO | 2025-06-23 | 2025-06-27 |  | Planned
87 | Sprint 4 Playback — full system walkthrough; SIT readiness sign-off | PMO / Sponsor | 2025-06-27 | 2025-06-27 |  | Planned
| PHASE 4 — SYSTEM INTEGRATION TESTING (SIT) (Late June – Mid July) | PwC | 2025-06-30 | 2025-07-11 |  | Planned
88 | 4.1 SIT Preparation & Training | PwC / Finance | 2025-06-30 | 2025-07-04 |  | Planned
89 | SIT tester onboarding & environment access (TEST env) | IT / PwC | 2025-06-30 | 2025-07-04 |  | Planned
90 | SIT test script walkthrough & tester briefing session | PwC | 2025-06-30 | 2025-07-04 |  | Planned
91 | Defect management tool setup (ADO / JIRA) — severity matrix confirmed | PwC PMO | 2025-06-30 | 2025-07-04 |  | Planned
92 | 4.2 SIT Execution — End-to-End Test Cycles | PwC | 2025-07-07 | 2025-07-18 |  | Planned
93 | SIT-01: Dimension & metadata integrity (all 7 dims, hierarchy rollups) | PwC | 2025-07-07 | 2025-07-11 |  | Planned
94 | SIT-02: All 20 calc rules — end-to-end compensation & WFP validation | PwC | 2025-07-07 | 2025-07-11 |  | Planned
95 | SIT-03: OPEX G&A driver validation — HC-linked & non-HC OPEX lines | PwC / Finance | 2025-07-07 | 2025-07-11 |  | Planned
96 | SIT-04: Integration data load testing — HRIS→EPM, ERP→EPM, Automate | PwC / IT | 2025-07-07 | 2025-07-11 |  | Planned
97 | SIT-05: Security & role-based access validation (all 4 roles) | IT Sec | 2025-07-07 | 2025-07-11 |  | Planned
98 | SIT-06: Forms, dashboards & Narrative Reporting functional testing | PwC | 2025-07-07 | 2025-07-11 |  | Planned
99 | SIT-07: Performance & concurrent-user load testing | PwC / IT | 2025-07-07 | 2025-07-11 |  | Planned
100 | SIT defect log — P1/P2 triage, assignment & resolution tracking | PwC PMO | 2025-07-07 | 2025-07-18 |  | Planned
101 | SIT regression testing — re-test after P1/P2 defect fixes | PwC | 2025-07-14 | 2025-07-18 |  | Planned
102 | Data conversion: UAT environment full data load & reconciliation | PwC / IT | 2025-07-14 | 2025-07-18 |  | Planned
▲ | ▲ SIT EXIT — 0 P1 defects; all 120 test cases executed; SIT sign-off | PwC PMO / Sponsor | 2025-07-18 | 2025-07-18 |  | Planned
| PHASE 5 — USER ACCEPTANCE TESTING (UAT) (July) | Finance / HR / FP&A | 2025-07-21 | 2025-08-01 |  | Planned
103 | 5.1 UAT Preparation | PwC / Finance | 2025-07-21 | 2025-07-25 |  | Planned
104 | UAT environment final validation — data quality & access check | IT / PwC | 2025-07-21 | 2025-07-25 |  | Planned
105 | UAT business scenario design — 60+ scenarios mapped to real planning cycles | PwC / Finance | 2025-07-21 | 2025-07-25 |  | Planned
106 | UAT tester training — business user orientation (Dept. Finance, HR BPs, FP&A) | PwC OCM | 2025-07-21 | 2025-07-25 |  | Planned
107 | 5.2 UAT Execution — Business-Led Validation | Finance / HR / FP&A | 2025-07-28 | 2025-08-01 |  | Planned
108 | UAT Cycle 1 — Position planning, submission & approval workflow | Dept. Finance Leads | 2025-07-28 | 2025-08-01 |  | Planned
109 | UAT Cycle 2 — New hire/attrition planning; comp calc validation | HR BPs | 2025-07-28 | 2025-08-01 |  | Planned
110 | UAT Cycle 3 — OPEX G&A by cost centre; variance vs Budget | FP&A | 2025-07-28 | 2025-08-01 |  | Planned
111 | UAT Cycle 4 — Management dashboards, infolets, Narrative Reporting | CFO Office / FP&A | 2025-07-28 | 2025-08-01 |  | Planned
112 | UAT defect log — P1/P2 resolution, regression, sign-off workflow | PwC PMO | 2025-07-28 | 2025-08-01 |  | Planned
113 | Go-Live readiness confirmation — business sign-off checklist | CFO / Sponsor | 2025-08-01 | 2025-08-01 |  | Planned
▲ | ▲ UAT SIGN-OFF — CFO & Sponsor signature; 0 P1 open; Go-Live authorized | CFO / Sponsor | 2025-08-01 | 2025-08-01 |  | Planned
| PHASE 6 — PRODUCTION RELEASE / GO-LIVE (August) | PwC / IT / Sponsor | 2025-08-04 | 2025-08-20 |  | Planned
114 | 6.1 Cutover Planning & Execution | PwC PMO / IT | 2025-08-04 | 2025-08-15 |  | Planned
115 | Cutover plan — detailed run-book with hour-by-hour task assignments | PwC PMO | 2025-08-04 | 2025-08-08 |  | Planned
116 | PROD environment final configuration & security hardening | IT / PwC | 2025-08-04 | 2025-08-08 |  | Planned
117 | Data conversion: PROD load — 3yr actuals, FY25 Budget/Forecast, positions | IT / PwC | 2025-08-04 | 2025-08-15 |  | Planned
118 | PROD data reconciliation — Finance sign-off vs source system | Finance / IT | 2025-08-11 | 2025-08-15 |  | Planned
119 | End-user training delivery — Dept. Planners, HR BPs, FP&A, CFO office | PwC OCM | 2025-08-04 | 2025-08-15 |  | Planned
120 | 6.2 Go / No-Go Governance | SteerCo / Sponsor | 2025-08-18 | 2025-08-20 |  | Planned
121 | Go / No-Go checklist review — 25-point criteria (tech, data, training, ops) | PwC PMO | 2025-08-18 | 2025-08-18 |  | Planned
122 | SteerCo Go / No-Go decision meeting | SteerCo / CIO / CFO | 2025-08-18 | 2025-08-18 |  | Planned
123 | Production system activation — EPM Automate scheduler live; user access granted | IT | 2025-08-19 | 2025-08-20 |  | Planned
▲ | ▲ GO-LIVE — Oracle EPM WFP & OPEX G&A PRODUCTION (Aug 20) | Sponsor / CIO / CFO | 2025-08-20 | 2025-08-20 |  | Planned
124 | 6.3 Go-Live Hypercare Entry (Weeks 1–2) | PwC | 2025-08-20 | 2025-09-05 |  | Planned
125 | Hypercare war room — daily triage, P1 4hr SLA, P2 1-day SLA | PwC | 2025-08-20 | 2025-09-05 |  | Planned
126 | Super-user floor support — Dept. Finance & FP&A desk-side assistance | PwC OCM | 2025-08-20 | 2025-09-05 |  | Planned
| PHASE 7 — PARALLEL RUN (Aug 21 – Oct 21) | Finance / PwC | 2025-08-21 | 2025-10-17 |  | Planned
127 | 7.1 Parallel Run Governance Setup | PwC PMO / Finance | 2025-08-21 | 2025-08-29 |  | Planned
128 | Parallel run governance framework — weekly checkpoints, escalation protocol | PMO | 2025-08-21 | 2025-08-22 |  | Planned
129 | Variance tolerance thresholds defined — $ tolerance & % FTE tolerance | Finance / PwC | 2025-08-21 | 2025-08-22 |  | Planned
130 | Parallel run test scope — processes, reports & key metrics to validate | Finance / PwC | 2025-08-21 | 2025-08-29 |  | Planned
131 | Parallel run reporting cadence — weekly variance report template | PwC PMO | 2025-08-21 | 2025-08-29 |  | Planned
132 | 7.2 Parallel Run Execution (8-week run) | Finance / PwC | 2025-09-01 | 2025-10-17 |  | Planned
133 | CUST_ParallelRunCheck: EPM vs legacy — position-level comparison (all depts) | Finance / PwC | 2025-09-01 | 2025-10-17 |  | Planned
134 | WFP output comparison — HC totals, compensation, FTE counts by dept | Finance | 2025-09-01 | 2025-10-17 |  | Planned
135 | OPEX G&A comparison — G&A line items, cost centre totals, BOR allocation | FP&A | 2025-09-01 | 2025-10-17 |  | Planned
136 | Reporting parity validation — EPM vs legacy management reports | Finance / FP&A | 2025-09-01 | 2025-10-17 |  | Planned
137 | Weekly variance analysis — root-cause investigation for threshold breaches | PwC / Finance | 2025-09-01 | 2025-10-17 |  | Planned
138 | Configuration fine-tuning — calc rule adjustments, metadata corrections | PwC | 2025-09-01 | 2025-10-10 |  | Planned
139 | Weekly Parallel Run Checkpoint meetings — variance review, decisions log | PMO / CFO / PwC | 2025-09-01 | 2025-10-17 |  | Planned
140 | 7.3 Parallel Run Deliverables & Exit | Finance / PMO | 2025-10-13 | 2025-10-17 |  | Planned
141 | Parallel run validation reports — weekly (8 reports) | PwC / Finance | 2025-09-01 | 2025-10-17 |  | Planned
142 | Variance analysis & remediation log — all breaches resolved or accepted | Finance / PwC | 2025-10-13 | 2025-10-17 |  | Planned
143 | Parallel run sign-off memo — CFO confirmation of EPM accuracy | CFO | 2025-10-17 | 2025-10-17 |  | Planned
144 | Final readiness confirmation for legacy system decommissioning | CIO / CFO | 2025-10-17 | 2025-10-17 |  | Planned
▲ | ▲ PARALLEL RUN EXIT — Legacy decommission authorized (Oct 21) | CFO / CIO / Sponsor | 2025-10-17 | 2025-10-17 |  | Planned
| PHASE 8 — EVOLVE / HYPERCARE & STEADY-STATE (Post Oct 21) | PwC / IT / Finance | 2025-10-20 | 2025-11-07 |  | Planned
145 | 8.1 Post-Go-Live & Post-Parallel-Run Review | PwC PMO | 2025-10-20 | 2025-10-24 |  | Planned
146 | Post-implementation review (PIR) — lessons learned, benefit realization | PMO / Sponsor | 2025-10-20 | 2025-10-24 |  | Planned
147 | Optimization backlog — enhancements, new features, user requests | Finance / IT | 2025-10-20 | 2025-10-24 |  | Planned
148 | 8.2 Hypercare Support Model | PwC / IT | 2025-10-27 | 2025-11-07 |  | Planned
149 | Break-fix SLA: P1 4hr, P2 1-day, P3 5-days — managed support | PwC | 2025-10-27 | 2025-11-07 |  | Planned
150 | Knowledge transfer — IT run-books, admin guides, support playbooks | PwC → IT | 2025-10-27 | 2025-11-07 |  | Planned
151 | Transition to steady-state AMS (Application Managed Services) | IT / PwC | 2025-11-03 | 2025-11-07 |  | Planned
152 | 8.3 Release 1b Scoping — Next Oracle EPM Modules | PwC / CIO / Finance | 2025-10-27 | 2025-11-07 |  | Planned
153 | FCCS (Financial Consolidation) — scoping & business case | PwC / Finance | 2025-10-27 | 2025-11-07 |  | Planned
154 | Narrative Reporting Phase 2 — board package automation scoping | PwC / Finance | 2025-10-27 | 2025-11-07 |  | Planned
155 | PCM / Profitability Cloud — scoping assessment | PwC / Finance | 2025-10-27 | 2025-11-07 |  | Planned
✏ Blue cells = editable Start/End dates (Gantt bars update automatically) ¦ ▲ = Milestone Gate ¦ ▼ = Today ¦ Duration column auto-calculates | [6 empty] | 2025-01-06: Design & Align; 2025-02-03: POC; 2025-03-03: Build Sprints; 2025-03-31: SIT; 2025-04-28: UAT; 2025-05-26: Go-Live; 2025-06-23: Parallel Run; 2025-07-21: Evolve/Hypercare; 2025-08-18: FY Planning

## Calc Rules Register
ORACLE EPM WFP — CALCULATION RULES REGISTER ¦ Sprint-Mapped ¦ 20 Rules Total
# | Rule Name | Type | Logic / Calculation | Dimensions | Script Type | Sprint | Status
── ORACLE STANDARD RULES (Sprint 1) ────────────────────────────────────────────────────────
1 | OEP_WFPCalcAll | Standard Oracle | Master rule — calculates all WFP data for all entities. Triggers compensation, HC aggregation, and period spread | All dimensions | None (std) | S1 | Active
2 | OEP_WFPClearAll | Standard Oracle | Clears all WFP data before full recalculation. Must precede WFPCalcAll to prevent double-counting | All | None (std) | S1 | Active
3 | OEP_WFPSpread | Standard Oracle | Spreads annual comp / HC values across monthly periods. Supports: even, actual-days, custom spread patterns | Period, Year | None (std) | S1 | Active
4 | OEP_WFPAggregateAll | Standard Oracle | Rolls department-level data up entity / division hierarchy for consolidated management reporting | Entity, Dept | None (std) | S1 | Active
5 | OEP_WFPCalcByEntity | Standard Oracle | Entity-scoped incremental calc. Used for single-entity updates without triggering full enterprise recalc | Entity, Scenario | None (std) | S1 | Active
── CUSTOM GROOVY RULES — COMPENSATION (Sprint 3) ───────────────────────────────────────────────
6 | CUST_SalaryEscalation | Custom Groovy | Merit escalation by Job Grade & Seniority Band. Reads Merit_Pct[Grade,Year] assumption table. Rolls forward from prior year actuals. Formula: Base_t = Base_t-1 × (1 + Merit_Pct[Grade,Year]) | Job Code, Grade, Period | Groovy | S3 | Dev
7 | CUST_COLAAdjustment | Custom Groovy | CPI-linked Cost of Living Adjustment applied as scalar multiplier. Separate COLA% for: (a) unionized positions, (b) non-unionized. Source: HR Annual Compensation Review table | Job Code, Union_Flag | Groovy | S3 | Dev
8 | CUST_BonusCalc | Custom Groovy | Short-Term Incentive (STI) pool: STI = Base_Salary × Bonus_Target_Pct × Perf_Modifier. Perf_Modifier is scenario-driven (Budget=1.0, Stretch=1.2, Downside=0.7). Accrued monthly, settled annually | Dept, Scenario | Groovy | S3 | Dev
9 | CUST_BenefitsLoading | Custom Groovy | Employer statutory burden: CPP (4.95% up to YMPE), EI (1.66× employee rate), WSIB (by NAICS class), Group Benefits (% of base), Pension match (% of base). Full-time vs part-time rate splits | Emp_Type, Province | Groovy | S3 | Dev
── CUSTOM GROOVY RULES — HEADCOUNT DRIVERS (Sprint 3–4) ───────────────────────────────────────
10 | CUST_VacancyRate | Custom Groovy | Vacancy Rate = (Approved_HC – Filled_HC) / Approved_HC. Computed at position → department → entity level. Used in OPEX comp savings calc | Position, Dept | Groovy | S3 | Dev
11 | CUST_FTEGapAnalysis | Custom Groovy | FTE Gap = Approved_HC – Filled_HC. Flags departments where Gap > 10% (configurable). Outputs alert flag to CFO dashboard infolet | Position, Entity | Groovy | S3 | Dev
12 | CUST_NewHireRamp | Custom Groovy | Partial-year cost: Cost = Annual_Salary × (Remaining_Months / 12) × Ramp_Pct[Hire_Month]. Ramp schedule loaded from assumption table (typically 50% M1, 75% M2, 100% M3+) | Position, Period | Groovy | S3 | Dev
13 | CUST_TerminationLogic | Custom Groovy | Zeroes compensation from effective termination date. Severance: Base_Salary × (Sev_Weeks/52). FTE count removed from effective month. Triggers CUST_FTEGapAnalysis re-run | Position, Period | Groovy | S3 | Dev
── CUSTOM GROOVY RULES — OPEX & INTEGRATION (Sprint 4–5) ─────────────────────────────────────
14 | CUST_ContractorCost | Custom Groovy | Contingent workforce: Cost = Bill_Rate × Contracted_Hours × Utilization_Pct. Separate from headcount-based comp. Aggregates into OPEX G&A P&L below personnel line | Cost_Centre, Period | Groovy | S4 | Dev
15 | CUST_ICPSpread | Custom Groovy | Below-the-line ICP separation: splits controllable OPEX from enterprise Investment Cost Pool allocations per BOR design. ICP treated as non-controllable by dept planners | Entity, Cost_Cat | Groovy | S4 | Dev
16 | CUST_BORAllocation | Custom Groovy | Book of Record pool → dept allocation. Keys: FTE% (workforce-related), AUM% (investment-related), Revenue% (business line). Allocation keys stored in assumption table | Dept, Alloc_Key | Groovy | S4 | Dev
17 | CUST_OPEXDriverCalc | Custom Groovy | Non-comp G&A: T&E = FTE × per_head_TE; IT = FTE × per_head_IT; Facilities = Sqft × Cost_per_Sqft; Training = FTE × Training_Budget. All per-head rates in assumption table | Cost_Cat, Dept | Groovy | S4 | Dev
18 | CUST_HCtoOPEXLink | Custom Groovy | Auto-populates OPEX G&A non-comp costs from confirmed WFP headcount plan. Ensures single source of truth between WFP module and Financial Statement (FS) module. Triggers on WFP plan approval | All WFP + FS dims | Groovy | S4 | Dev
19 | CUST_ScenarioVariance | Custom Groovy | Variance engine: Budget vs Forecast vs Actual. Outputs: $ variance, % variance, FTE variance. Triggers commentary prompt flag where threshold exceeded (>5% or >$50K) | Scenario, Period | Groovy | S4 | Dev
20 | CUST_ParallelRunCheck | Custom Groovy | Parallel run validation: EPM output vs legacy spreadsheet at position level. Flags rows with $ variance > $5K or FTE variance > 2%. Produces reconciliation report for weekly checkpoint | All | Groovy | S7 (SIT) | Planned

## Milestones & RACI
MILESTONE GATES, EXIT CRITERIA & RACI MATRIX
Milestone | Description | Target Date | Phase | Exit Criteria | Owner / Approver
▲ Design Gate | KDDs, RTM, Future-State Architecture, Config Workbook & Instance Strategy approved | 28-Feb-25 | Design & Align | All KDDs signed off; RTM baselined in tool; Config Workbook v1.0 approved; Instance Management Strategy confirmed; POC sign-off received | Sponsor / CFO
▲ Build Entry | POC validated; design freeze; sprint backlog baselined and RICE-prioritized | 03-Mar-25 | Build | POC findings incorporated into design; sprint backlog groomed; environment DEV live; RTM traceability confirmed | PwC PMO
▲ Sprint 1 Complete | Foundation, environment, std calc rules & position master | 28-Mar-25 | Sprint 1 | 5 std rules run error-free; all dims loaded; PROD env provisioned; position master loaded (500+ positions); S1 playback accepted | Finance / IT
▲ Sprint 2 Complete | Integrations, workflows, historical data loaded | 25-Apr-25 | Sprint 2 | HRIS→EPM live; 3yr actuals reconciled; GL actuals loading; planning calendar functional; S2 playback accepted | Finance / IT
▲ Sprint 3 Complete | All compensation & HC Groovy calc rules unit-tested | 30-May-25 | Sprint 3 | 7 Groovy comp rules unit-tested; comp calc vs HR actuals ±1%; assumption tables complete; S3 playback accepted | Finance / HR
▲ Sprint 4 Complete / SIT Entry | All build complete; SIT scripts approved; TEST env loaded | 27-Jun-25 | Sprint 4 | 20 calc rules complete; all forms/dashboards built; SIT scripts approved; TEST env data reconciled; S4 playback accepted | PMO / Sponsor
▲ SIT Exit | All 120+ test cases executed; 0 P1 defects open | 18-Jul-25 | SIT | 0 P1 defects open; P2 remediation plan agreed; UAT env data loaded; regression passed; RTM updated | PwC PMO / Sponsor
▲ UAT Sign-Off | Business-led validation complete; Go-Live authorized | 01-Aug-25 | UAT | 100% UAT scripts executed; 0 P1 open; P2 resolution plan agreed; CFO sign-off obtained; Go-Live checklist approved | CFO / Sponsor
▲ Go-Live | Oracle EPM WFP & OPEX G&A PRODUCTION live | 20-Aug-25 | Release | PROD stable; all users active; EPM Automate scheduler running; hypercare war room open; no P1 blocking issues | Sponsor / CIO / CFO
▲ Parallel Run Exit | Legacy system decommission authorized | 21-Oct-25 | Parallel Run | 8 weekly checkpoint reports complete; 0 unresolved P1 variances; CFO parallel run sign-off; legacy decommission plan approved | CFO / CIO / Sponsor
▲ Steady-State | Knowledge transferred; AMS transition complete | 07-Nov-25 | Evolve | Run-books handed over; IT support team trained; Release 1b backlog groomed; PIR complete | CIO / IT Mgr
RACI MATRIX — KEY WORKSTREAMS
Workstream | PwC Lead | Client Sponsor | CFO / FP&A | IT / Infra | HR / HRBP
Design & Align | R/A | A | C | I | C
POC Build & Validation | R/A | C | C | I | I
Sprint 1: Env & Foundation | R | I | I | A/R | I
Sprint 2: Workflows & Integration | R | A | C | A/R | C
Sprint 3: Groovy Calc Rules | R/A | I | C | I | I
Sprint 4: Reporting & SIT Prep | R | C | A | C | I
SIT Execution | R/A | I | C | C | I
UAT Execution | C | A | R | C | R
Training & OCM | R | C | A | I | C
Cutover & Go-Live | R | A | C | R | C
Parallel Run Execution | R | A | R | C | I
Parallel Run Governance | C | A | A/R | I | I
Evolve / Hypercare Support | R/A | I | I | C | I
Knowledge Transfer to IT | R → C | I | I | A/R | I
Release 1b Scoping | R | C | A | C | I
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed ¦ R/A = Responsible & Accountable